## Sheet1
삭제 Del | 작업활동 및 내용 Work & Contents | 유해위험요인 및 환경측면 영향 Hazard & Risk | EHS | 피해형태 및 환경영향 Damage & Effect | 위험성 Risk Rate | 위험성 Risk Rate.1 | 위험성 Risk Rate.2 | 등급 Rate | 개선대책 및 세부관리방안 Corrective Action | 개선담당자 Responsibility | 개선일자 Action Date | 위험성 Risk Rate | 위험성 Risk Rate.1 | 위험성 Risk Rate.2 | 등급 Rate | Unnamed: 16 | 원본파일 | 원본시트 | 구분 | 코드
삭제 Del | 작업활동 및 내용 Work & Contents | 유해위험요인 및 환경측면 영향 Hazard & Risk | EHS | 피해형태 및 환경영향 Damage & Effect | 빈도 Risk Rate | 강도 Severity | T | 등급 Rate | 개선대책 및 세부관리방안 Corrective Action | 개선담당자 Responsibility | 개선일자 Action Date | 빈도 Likelihood | 강도 Severity | T | 등급 Rate |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Collision with other vehicle, equipment or transport vehicle during transport due to failure to check transport route plan | S | Personal / Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and ensure equipment possess operation permit 3) Inspect and verify transportation route in advance 4) Assign trained flagman or escort vehicle during transport | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Transport vehicle hitting or striking existing site structure due to overspeeding / non observance of traffic rules | S | Property | 2 | 3 | 6 | C | 1) Vehicle follow 20 kph speed limit and other site traffic rules / regulations 2) Vehicle pass at designated transport route plan | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Failure to inspect the ground condition of the transport route resulting in overturning of transport vehicle | S | Personal / Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and ensure equipment possess operation permit 3) Inspect and verify transportation route in advance 4) Ensure ground for transport route rerlatively level & smooth and potholes covered | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Material or load hitting traffic signage or other existing structure due to failure to inspect the transport route | S | Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and ensure equipment possess operation permit 3) Inspect and verify transportation route in advance | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Failure to assign or provide trained flagman resulting in collision with other vehicle or equipment | S | Personal / Property | 2 | 3 | 6 | C | 1) Assign trained flagman on both front and rear part of the transport vehicle 2) Assign escort vehicle equipped with megaphone if available | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Collision with existing structure, vehicle, site personnel while manoeuvring or reversing due to absence of trained flagman | S | Personal / Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and verify transportation route in advance 3) Check and verify transport vehicle reverse alarm, hazard lights, other safety device and assign trained flagman on both front and rear part of the vehicle 4) Assign flagman in choke points to control traffic during the time of transport | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Interference with other site activities causing congestion along the access road and resulting in traffic accident | S | Personal / Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and verify transportation route in advance 3) Assign flagman in choke points to control traffic during the time of transport 4) Schedule transport of materials during non-peak time to avoid congesting the access road | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Material fall during transport due to absence or poor lashing / securing to trailer bed | S | Personal / Property | 2 | 3 | 6 | C | 1) Materials placed on rack or box and tied properly 2) Materials properly secured with lashing belt | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Material fall due to absence of wood wedge resulting in material rolling from the transport bed | S | Property | 2 | 3 | 6 | C | 1) Materials placed on original metal or wood rack or box and tied properly 2) Materials properly secured with lashing belt | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Failure to check the height limitation resulting in material hitting low level overhead structure / electrical cable | S | Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and ensure equipment possess operation permit 3) Inspect and verify transportation route in advance and height of existing structure crossing the access road | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Failure to provide appropriate cradle or support when transporting bulky materials resulting in material fall | S | Property | 2 | 3 | 6 | C | 1) Avoid removing any cradle / wood support connected to the material that will be transported 2) Materials properly secured to trailer bed with lashing belt using material transport checklist | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Material falling from trailer bed due to exceeding load capacity of transport vehicle | S | Property | 2 | 3 | 6 | C | 1) Conduct inspection of materials more than 10 Tons in weight 2) Check material gross weight from manifest / receipt before loading to trailer bed 3) Check trailer bed condition to include tyre conditions after placing material on trailer bed 4) Materials properly lashed & secure to trailer bed before transport using material transport checklist | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Vehicle colliding with the material being transported due to absence of bunting, signage or escort vehicle | S | Property | 2 | 3 | 6 | C | 1) Vehicle follow 20 kph speed limit and other site traffic rules / regulations 2) Vehicle pass at designated transport route plan 3) Provide escort vehicle at rear of transport vehicle 4) When tranporting bulky / long materials, provide and place safety signage / buntings along the material edge that extends from the transport vehicle 5) Assign trained flagman to assist traffic for other vehicle / equipment during transport | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Struck by materials due to improper passing | S | Physical | 3 | 4 | 12 | B | 1) Assign enough personnel for the activity 2) Avoid throwing the materials | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Material fall due to unsafe passing | S | Property | 3 | 4 | 12 | B | 1) Personnel to wear proper PPE, leather or rubber coated hand gloves 2) Avoid throwing materials and pass by hand only | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Fall on the same floor due to scattered materials | S | Physical / property | 3 | 3 | 9 | C | 1) Conduct housekeeping and remove loose materials from the ground 2) Ensure proper cable management and hang them overhead | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Back / hand pain due to repititive movement | S | Physical | 3 | 3 | 9 | C | 1) Lift materials less than 25 kilos and use buddy system 2) Provide frequent rest breaks to break monotony of movement 3) Utilize mechanical lifting equipment, if available such as mechanical pallet jack | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Personnel fall due to unstable ground conditions along the access | S | Physical / property | 2 | 4 | 8 | C | 1) Check ground condition, compact and level 2) Personnel to wear proper basic PPE 3) Secure safe access / passage ways for workers | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Material fall due to unsafe and improper stacking | S | Physical / property | 2 | 3 | 6 | C | 1) Ensure solid and level base / ground 2) Check material condition on proper and safe stacking 3) Compact and level the ground if possible 4) Avoid stacking materials more than 1.5 meters high | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Falling due to insufficient / improper / unsafe slinging & dogging of lifting gears to material | S | Physical / Pproperty | 2 | 3 | 6 | C | 1) Check safety capacity lifting gears and tackles that will be use 2) Materials lifted and transported properly lashed / binded by skilled worker 3) Ensure material box are 3rd party certified with SWL visibly painted on them 4) Check equipment safe lifting capacity before use | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Material fall during stacking due to non observance of height limitation & not securing the materials properly | S | Property | 2 | 3 | 6 | C | 1) Use racks and arrange the materials according to its weight, height, dimension and configuration. 2) Avoid stacking materials more than 1.5 meters in heights 3) Provide or use wood wedge for materials susceptible to roll 4) Check straps / lashing of materials and provide additional lashing if necessary. | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Using unsafe, damage, improper support for the stacked materials | S | Property | 2 | 3 | 6 | C | 1) Use racks and arrange the materials according to its weight, height, dimension and configuration. 2) Avoid stacking materials more than 1.5 meters in heights 3) Provide or use wood wedge for materials susceptible to roll 4) Check straps / lashing of materials and provide additional lashing if necessary. | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Material fall due to poor housekeeping at laydown area and not observing load height | S | Property | 1 | 2 | 2 | E | 1) Check proper storage of materials where the unit weight is above of 10 tons based on material specification and manufacturer guideline 2) Check safety capacity of lifting gears and tackles 3) Ensure materials are lashed or secured by skilled workers 4) Ensure material box are 3rd party certified with SWL visibly painted on them 5) Check lift equipment safety capacity before using 6) Ensure solid and level ground condition 7) Ensure proper housekeeping at material laydown / storage area | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Contact with high voltage or energized cable during transport of pipe resulting in electric shock / electrocution | S | Personnel / property | 2 | 4 | 8 | C | 1) Provide appropriate protection cover for high-voltage / energized cable at site 2) Remove or relocate site obstruction in coordination with relevant department | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Collision with other vehicle, equipment or transport vehicle during transport due to failure to check transport route plan | S | Personal / Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and ensure equipment possess operation permit 3) Inspect and verify transportation route in advance 4) Assign trained flagman or escort vehicle during transport | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Transport vehicle hitting or striking existing site structure due to overspeeding / non observance of traffic rules | S | Property | 2 | 3 | 6 | C | 1) Vehicle follow 20 kph speed limit and other site traffic rules / regulations 2) Vehicle pass at designated transport route plan | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Failure to inspect the ground condition of the transport route resulting in overturning of transport vehicle | S | Personal / Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and ensure equipment possess operation permit 3) Inspect and verify transportation route in advance 4) Ensure ground for transport route rerlatively level & smooth and potholes covered | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Material or load hitting traffic signage or other existing structure due to failure to inspect the transport route | S | Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and ensure equipment possess operation permit 3) Inspect and verify transportation route in advance | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Failure to assign or provide trained flagman resulting in collision with other vehicle or equipment | S | Personal / Property | 2 | 3 | 6 | C | 1) Assign trained flagman on both front and rear part of the transport vehicle 2) Assign escort vehicle equipped with megaphone if available | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Collision with existing structure, vehicle, site personnel while manoeuvring or reversing due to absence of trained flagman | S | Personal / Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and verify transportation route in advance 3) Check and verify transport vehicle reverse alarm, hazard lights, other safety device and assign trained flagman on both front and rear part of the vehicle 4) Assign flagman in choke points to control traffic during the time of transport | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Interference with other site activities causing congestion along the access road and resulting in traffic accident | S | Personal / Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and verify transportation route in advance 3) Assign flagman in choke points to control traffic during the time of transport 4) Schedule transport of materials during non-peak time to avoid congesting the access road | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Material fall during transport due to absence or poor lashing / securing to trailer bed | S | Personal / Property | 2 | 3 | 6 | C | 1) Materials placed on rack or box and tied properly 2) Materials properly secured with lashing belt | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Material fall due to absence of wood wedge resulting in material rolling from the transport bed | S | Property | 2 | 3 | 6 | C | 1) Materials placed on original metal or wood rack or box and tied properly 2) Materials properly secured with lashing belt | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Failure to check the height limitation resulting in material hitting low level overhead structure / electrical cable | S | Property | 2 | 3 | 6 | C | 1) Prepare or establish a transportation route plan 2) Inspect and ensure equipment possess operation permit 3) Inspect and verify transportation route in advance and height of existing structure crossing the access road | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Failure to provide appropriate cradle or support when transporting bulky materials resulting in material fall | S | Property | 2 | 3 | 6 | C | 1) Avoid removing any cradle / wood support connected to the material that will be transported 2) Materials properly secured to trailer bed with lashing belt using material transport checklist | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Material falling from trailer bed due to exceeding load capacity of transport vehicle | S | Property | 2 | 3 | 6 | C | 1) Conduct inspection of materials more than 10 Tons in weight 2) Check material gross weight from manifest / receipt before loading to trailer bed 3) Check trailer bed condition to include tyre conditions after placing material on trailer bed 4) Materials properly lashed & secure to trailer bed before transport using material transport checklist | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Tansportation of materials | Vehicle colliding with the material being transported due to absence of bunting, signage or escort vehicle | S | Property | 2 | 3 | 6 | C | 1) Vehicle follow 20 kph speed limit and other site traffic rules / regulations 2) Vehicle pass at designated transport route plan 3) Provide escort vehicle at rear of transport vehicle 4) When tranporting bulky / long materials, provide and place safety signage / buntings along the material edge that extends from the transport vehicle 5) Assign trained flagman to assist traffic for other vehicle / equipment during transport | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Struck by materials due to improper passing | S | Physical | 3 | 4 | 12 | B | 1) Assign enough personnel for the activity 2) Avoid throwing the materials | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Material fall due to unsafe passing | S | Property | 3 | 4 | 12 | B | 1) Personnel to wear proper PPE, leather or rubber coated hand gloves 2) Avoid throwing materials and pass by hand only | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Fall on the same floor due to scattered materials | S | Physical / property | 3 | 3 | 9 | C | 1) Conduct housekeeping and remove loose materials from the ground 2) Ensure proper cable management and hang them overhead | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Back / hand pain due to repititive movement | S | Physical | 3 | 3 | 9 | C | 1) Lift materials less than 25 kilos and use buddy system 2) Provide frequent rest breaks to break monotony of movement 3) Utilize mechanical lifting equipment, if available such as mechanical pallet jack | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Personnel fall due to unstable ground conditions along the access | S | Physical / property | 2 | 4 | 8 | C | 1) Check ground condition, compact and level 2) Personnel to wear proper basic PPE 3) Secure safe access / passage ways for workers | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Material fall due to unsafe and improper stacking | S | Physical / property | 2 | 3 | 6 | C | 1) Ensure solid and level base / ground 2) Check material condition on proper and safe stacking 3) Compact and level the ground if possible 4) Avoid stacking materials more than 1.5 meters high | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Falling due to insufficient / improper / unsafe slinging & dogging of lifting gears to material | S | Physical / Pproperty | 2 | 3 | 6 | C | 1) Check safety capacity lifting gears and tackles that will be use 2) Materials lifted and transported properly lashed / binded by skilled worker 3) Ensure material box are 3rd party certified with SWL visibly painted on them 4) Check equipment safe lifting capacity before use | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Material fall during stacking due to non observance of height limitation & not securing the materials properly | S | Property | 2 | 3 | 6 | C | 1) Use racks and arrange the materials according to its weight, height, dimension and configuration. 2) Avoid stacking materials more than 1.5 meters in heights 3) Provide or use wood wedge for materials susceptible to roll 4) Check straps / lashing of materials and provide additional lashing if necessary. | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Using unsafe, damage, improper support for the stacked materials | S | Property | 2 | 3 | 6 | C | 1) Use racks and arrange the materials according to its weight, height, dimension and configuration. 2) Avoid stacking materials more than 1.5 meters in heights 3) Provide or use wood wedge for materials susceptible to roll 4) Check straps / lashing of materials and provide additional lashing if necessary. | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Material fall due to poor housekeeping at laydown area and not observing load height | S | Property | 1 | 2 | 2 | E | 1) Check proper storage of materials where the unit weight is above of 10 tons based on material specification and manufacturer guideline 2) Check safety capacity of lifting gears and tackles 3) Ensure materials are lashed or secured by skilled workers 4) Ensure material box are 3rd party certified with SWL visibly painted on them 5) Check lift equipment safety capacity before using 6) Ensure solid and level ground condition 7) Ensure proper housekeeping at material laydown / storage area | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Material Handling / carrying materials | Contact with high voltage or energized cable during transport of pipe resulting in electric shock / electrocution | S | Personnel / property | 2 | 4 | 8 | C | 1) Provide appropriate protection cover for high-voltage / energized cable at site 2) Remove or relocate site obstruction in coordination with relevant department | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Overturning of crane after setting too close to excavation edge | S | Physical / property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Check the ground settlement of outrigger support during setting-up of mobile crane 4) Set outriggers at least 2 meters from the edge of excavation area 5) Assign 3rd party certified & competent crane operator | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Overturning of mobile crane due to ground settlement of out-rigger's support during lifting | S | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Check the ground settlement of outrigger support during setting-up of mobile crane 4) Barricade the lifting area and prohibit entry through strict supervision 5) Prepare lifting plan for critical lift, tandem lifting and heavy lifting activity | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Overturning / tumbling of mobile crane due to collapse of outrigger after failing to install the outrigger locking pins | S | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Check and ensure outrigger locking pins are placed | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Overturning / tumbling of mobile crane due to failure to fully extend the crane outriggers | S | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Check and ensure outrigger are fully extended and locking pins are engaged | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Overturning / tumbling of mobile crane due to equipment tyres not elevated and outrigger not properly set | S | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Check & inspect set-up of crane before start of lifting activity, tyres of mobile crane elevated at least 1 inch from the ground | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Overturning of crane during lifting after bypassing the load capacity or boom radius | S | Physical / Property | 3 | 4 | 12 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Check crane safety device including overload limiter and limit switch 3) Prepare lifting plan for critical lift, tandem lifting and heavy lifting activity 4) Assign 3rd party certified & competent crane operator | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Material fall when web sling was cut after being in contact with the sharp edge of material being lifted | S | Physical / Property | 2 | 4 | 8 | C | 1)Check the lifting gears to be used before any lifting activity 2) Provide softener or pipe sleeve in areas where web sling is in contact with the sharp edge of the load 3) Lift using the lifting lugs provided 4) Barricade the lifting area and prohibit entry during lifting activity | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Material fall due to breaking of wire rope during lifting | S | Physical / Property | 2 | 4 | 8 | C | 1) Inspect and check all lifting gears to be used before the lifting activity start 2) Prohibit anybody from entering the lifting area 3) Conduct high risk work last minute risk assessment 4) Assign 3rd party certified & competent rigger | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Material fall during lifting due to poor welding connection of lifting lug | S | Physical / Property | 2 | 5 | 10 | B | 1) Conduct high risk work last minute risk assessment 2) Conduct welding lug inspection using MT / PT 3) Prohibit anybody from entering the lifting area 4) Strict supervision and barricade the lifting area | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Material fall during lifting after using damaged lifting tackles (shackles) | S | Physical / Property | 3 | 4 | 12 | B | 1) Inspect all lifting tackles (shackles) to be used before the lifting activity start, inspection certificate 2) Prohibit anybody from entering the lifting area 3) Conduct high risk work last minute risk assessment 4) Assign 3rd party certified & competent rigger | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Material fall due to breaking of web sling during lifting | S | Physical / Property | 3 | 4 | 12 | B | 1) Inspect all web slings to be used before the lifting activity start, inspection certificate 2) Prohibit anybody from entering the lifting area 3) Check SWL of lifting gears compared to the material to be lifted 4) Conduct high risk work last minute risk assessment 5) Assign 3rd party certified & competent rigger | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Material fall when lifting gears is detached from the hook block due to absence of safety latch | S | Physical / Property | 1 | 4 | 4 | D | 1) Check equipment using the daily equipment checklist before use 2) Check the safety latch of the main hook block / auxilliary hook to be in good working condition 3) High-risk work safety pre-qualification 4) Barricade and strictly control personnel from entering the lifting area | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Material fall due to loosened crane wire rope caused by improper / loosened revving | S | Physical / Property | 1 | 4 | 4 | D | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Check and inspect the equipment daily using the equipment checklist before use 3) Check crane safety device (limit switch, overload limit switch, crane monitor, etc) 4) Assign 3rd party certified & competent crane operator | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Material fall or personnel strike by load due to uncontrolled lowering of load | S | Physical / Property | 1 | 4 | 4 | D | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the equipment daily using the equipment checklist before use 3) Check crane safety device (limit switch, overload limit switch, crane monitor, etc) 4) Assign 3rd party certified & competent crane operator | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Material fall or personnel strike by load when lifting during strong wind | S | Physical / Property | 3 | 4 | 12 | B | 1) Strictly monitor the weather condition (wind condition), suspend lifting during strong winds 2) Follow lifting restriction depending on wind speed | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Personnel strike or hit by material during lifting due to absence of flagman | S | Physical / Property | 1 | 4 | 4 | D | 1) Assign trained flagman and provide megaphone to be used during high risk lifting activity 2) Restrict entry of personnel inside lifting area 3) Provide barricade & signage along the perimeter of the lifting area | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Personnel hit or strike by load due to uncontrolled lifting / absence of tagline or guide rope | S | Physical / Property | 3 | 4 | 12 | B | 1) Assign competent worker to assist in lifting activity, holding the tag line or guide rope 2) Use minimum of 2-16mm diameter pp rope at least 10 meters in length or more as guide rope 3) Use megaphone or whistle to control people in the vicinity during lifting activity | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Bending of crane boom while lifting heavy materials due to failure or not providing overload limit switch | S | Property | 3 | 4 | 12 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Check and inspect the equipment daily using the equipment checklist before use 3) Check crane safety device (limit switch, overload limit switch, crane monitor, etc) 4) Assign 3rd party certified & competent crane operator | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Absence of barricade along the crane working radius injuring other personnel when the material accidentally falls | S | Physical / Property | 2 | 5 | 10 | B | 1) Provide barricade & signage along the perimeter of the crane working radius 2) Assign trained flagman 3) Strictly supervise lifting activity 4) Conduct LMRA before starting any high risk lifting activity | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Material fall due to improper / unsafe handling | S | Physical / property | 3 | 3 | 9 | C | 1) Personnel to wear proper PPE, leather or rubber coated hand gloves 2) Avoid throwing materials and pass by hand only 3) Assign enough personnel for the activity | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Eletrocution / electric shock caused by touching damaged, frayed, uninsulated electrical extension cable | S | Physical | 2 | 3 | 6 | C | 1) Check condition of power tool to include its electrical cables / connections 2) Power tool using 3P cord | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Electrocution / electric shock due to absence of ELCB / GFCI for the electrical cable connection | S | Physical | 2 | 4 | 8 | C | 1) Use compatibler outlet and plug for electrical connection 2) Ensure socket outlet of electrical distribution board equipped with 30mA ELCB / GFCI / RCB 3) Conduct regular inspection of all distribution board | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | General Lifting Activity | Fall on the same level due to poor housekeeping and material / cable management in the work area | S | Physical / property | 3 | 3 | 9 | C | 1) Conduct regular housekeeping and material arrangement in the work area 2) Manage electrical cables properly and hang them overhead 3) Remove waste materials immediately | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Duct Installation | Overturning of mobile crane due to ground settlement of out-rigger's support during lifting | S | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Barricade lifting area and prohibit entry through strict supervision | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Duct Installation | Overturning / tumbling of mobile crane due to collapse of outrigger after failing to install the outrigger locking pins | S | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Check and ensure outrigger locking pins are placed | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Duct Installation | Material fall due to breaking of web sling during lifting | S | Physical / Property | 3 | 4 | 12 | B | 1) Inspect all web slings to be used before the lifting activity start, inspection certificate 2) Prohibit anybody from entering the lifting area 3) Check SWL of lifting gears compared to the material to be lifted 4) Conduct high risk work last minute risk assessment 5) Assign 3rd party certified & competent rigger | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Duct Installation | Falling of materials because of failure of emergency stop switch | S | Physical / Property | 3 | 3 | 9 | C | 1) Check materials pulling up area interference 2) Check accessories before work 3) Prohibit unauthorized person at the lifting work area | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Personnel fall caused by not wearing safety harness | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lifeline 2) Comply with 100% tie-off 3) Before height work, practice double hook demonstration 4) Workers must attend Work at Heights safety training | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Personnel fall due to absence of safety rail | S | Physical | 3 | 5 | 15 | B | 1) Install safety rail and wear / use full body harness for worker in elevated area 2) Provide additional temporary lifeline if possible | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Fall of materials due to of absence of toe board | S | Physical / Property | 3 | 4 | 12 | B | 1) Conduct regular housekeeping and remove all loose materials from platform 2) Install toe board along the edge of the working platform | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Fall due to unsecured/incomplete planking of working platform | S | Physical / Property | 3 | 5 | 15 | B | 1) Secure all wood planks with board clamp & maintain proper lapping 2) Install wood planks with maximum of 1 inch gap between planks | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Scaffold collapse due to unsafe connection of scaffold components | S | Physical / Property | 2 | 4 | 8 | C | 1) Check the connection of scaffold materials 2) Check the quality of scaffold materials used | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Personnel fall due to absence of proper access on the scaffold structure | S | Physical | 3 | 3 | 9 | C | 1) Scaffold structure regularly inspected by certified scaffold inspector 2) Scaffold tag attached and regularly updated 3) Access ladder inspected and ladder tag attached 4) Follow scaffold guidelines when installing access ladder | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Fall of worker along edge of scaffold structure due to absence of proper working platform / cantilever platform | S | Physical | 2 | 4 | 8 | C | 1) Manage the temporary structure using scaffold tag 2) Install guardrail along the edge of scaffold platform 3) Provide lifeline whenever applicable or necessary 4) Ensure regular inspection of all working platform on the scaffold structure | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Personnel fall while climbing ladder and carrying materials | S | Physical / property | 3 | 4 | 12 | B | 1) Provide staircase instead of straight ladder as access to scaffold structure 2) Use appropriate lifting device in case materials needed to be brought on the scaffold platform 3) Maintain 3-point contact when climbing the ladder 4) Workers to attend work at heights safety training | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Personnel fall when worker over extend his body outside the scaffold platform | S | Physical | 3 | 5 | 15 | B | 1) Workers to attend work at heights safety training 2) Personnel to wear basic PPE to include full body harness and maintain 100% tie-off 3) Provide lifeline whenever necessary or applicable 4) Install cantilever platform wherever required | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Personnel fall when working on unsecured platform | S | Physical / property | 3 | 5 | 15 | B | 1) Scaffold structure inspected by certified scaffold inspector 2) Provide the necessary scaffold tag 3) Workers to attend work at heights safety training 4) Personnel to wear basic PPE to include full body harness and maintain 100% tie-off | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Personnel fall when working on uninspected scaffold structure | S | Physical | 2 | 5 | 10 | B | 1) Scaffold structure inspected by certified scaffold inspector 2) Provide the necessary scaffold tag 3) Workers to attend work at heights safety training 4) Personnel to wear basic PPE to include full body harness and maintain 100% tie-off | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Falling or overturning of mobile scaffold when moving while personnel are on top | S | Physical / property | 3 | 5 | 15 | B | 1) Workers to attend work at heights safety training 2) Ensure strict supervision when using mobile scaffold 3) Personnel to wear and use the necessary PPE | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Personnel fall when working on mobile scaffold with caster wheels not engaged or locked | S | Physical / property | 3 | 4 | 12 | B | 1) Mobile scaffold inspected by certified scaffold inspector 2) Provide scaffold tag to mobile scaffold 3) Inspect and check condition of caster wheels | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Material fall after leaving them unattended from the scaffold | S | Physical / property | 2 | 4 | 8 | C | 1) Secure all materials with PP rope or remove unused materials from the platform regularly 2) Conduct regular housekeeping | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
false | Cladding Installation | Overturning or tumbling due to poor illumination / lighting | S | Physical | 3 | 3 | 9 | C | 1) Provide enoguh lighting / illumination at the work area 2) Follow OSHA illumination standards for the work place 3) Ensure safe passage / access way for workers | Byungchul Lee | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 기계공사 (플랜트).xls | Sheet1
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | EHS | E
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | EHS | H
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | EHS | S
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 빈도 Risk Rate | 1
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 빈도 Risk Rate | 2
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 빈도 Risk Rate | 3
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 빈도 Risk Rate | 4
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 빈도 Risk Rate | 5
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 강도 Severity | 1
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 강도 Severity | 2
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 강도 Severity | 3
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 강도 Severity | 4
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 강도 Severity | 5
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 빈도 Likelihood | 1
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 빈도 Likelihood | 2
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 빈도 Likelihood | 3
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 빈도 Likelihood | 4
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 빈도 Likelihood | 5
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 강도 Severity | 1
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 강도 Severity | 2
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 강도 Severity | 3
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 강도 Severity | 4
[17 empty] | SWRO 기계공사 (플랜트).xls | 코드목록 | 강도 Severity | 5
삭제 Del | 작업활동 및 내용 Work & Contents | 유해위험요인 및 환경측면 영향 Hazard & Risk | EHS | 피해형태 및 환경영향 Damage & Effect | 빈도 Risk Rate | 강도 Severity | T | 등급 Rate | 개선대책 및 세부관리방안 Corrective Action | 개선담당자 Responsibility | 개선일자 Action Date | 빈도 Likelihood | 강도 Severity | T | 등급 Rate |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Electricity | Electrocution / electric shock due to absence of grounding for distribution board | E | Physical | 2 | 3 | 6 | C | 1) Install copper grounding rod and connect body grounding of distribution board properly 2) Check resistance of copper grounding and must be below 5 ohms | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Electricity | Electric shock when worker connect the socket to the outlet of distribution board | E | Physical | 2 | 5 | 10 | B | 1) Install fence, lock system and only Authorized personnel only 2) Regularly check the condition of the socket outlets 3) regularly check the working condition of the ELCB / GFCI 4) Install dead front type covers to hide wiring connections | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Electricity | Electric shock caused by inadequate insulation and absence of ELCB | E | Physical | 3 | 5 | 15 | B | 1) Inspect if cable is 3-phase or double insulated 2) Check power source if provided with 30mA ELCB 3) Inspect if electrical DB is properly grounded | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Electricity | Electrocution / electric shock caused while conducting welding activity | E | Physical | 3 | 4 | 12 | B | 1) Insulate cable terminals with insulation tapes or covers 2) Set automatic shock protector and wear proper PPE | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Electricity | Slip / fall of worker on the same level due to poor cable management | E | Physical | 3 | 3 | 9 | C | 1) Arrange all electrical and welding cable in the work area 2) Coil and hang cables overhead using insulated post / S-bar | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Civil | Collapse of slope caused by unstable ground and change of ground-water level | E | Physical / Property | 2 | 4 | 8 | C | 1) Follow proper sloping depending on soil classification 2) Provide dewatering equipment to remove accumulated water and prevent scouring of excavation base 3) Install safety net for the excavation side slope | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Civil | Fire / explosion when hitting underground utilities during excavation | E | Physical / Property | 3 | 2 | 6 | C | 1) Check the location of underground utility before starting work 2) Relocate electric line, communication and gas line | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Civil | Personnel fall to excavation due to absence of fall prevention facility | E | Physical | 2 | 3 | 6 | C | 1) Install appropriate barricade along the perimeter of the excavation 2) Post warning / safety signage prominently | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Civil | Tumbling / falling due absence of proper access to excavation | E | Physical | 2 | 3 | 6 | C | 1) Provide proper and safe temporary access leading to excavated area 2) Provide handrails along the side of the temporary access | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Civil | Vehicle / equipment fall to excavation due to inadequate fall prevention facility / traffic & warning signage | E | Physical / Property | 2 | 3 | 6 | C | 1) Install earth dike / berm along the excavation edge 2) Provide safety / warning signage and traffic blinkers | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Fence | Overturning / fall of temporary fence due to strong wind during installation | E | Physical / Property | 1 | 2 | 2 | E | 1) Provide enough support during installation of temporary fence 2) Strictly supervise activity and suspend in case of strong wind condition | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Fence | Fall while using straight ladder when installing the temporary fence | E | Physical | 1 | 3 | 3 | D | 1) Use step / A-type ladder instead of straight ladder 2) Assign worker to support and hold the step ladder in place 3) Provide outrigger support for A-type ladder | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Fence | Cut / laceration while handling / installing the temporary fence | E | Physical | 2 | 2 | 4 | D | 1) Use proper hand gloves 2) Assign enough number of workers to install the temporary fence | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Temporary Fence | Back / hand pain due to repititive movement / manual handling of materials | E | Physical | 3 | 3 | 9 | C | 1) Lift materials less than 25 kilos 2) Provide frequent rest breaks to break monotony of movement | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Overturning of crane after setting too close to excavation edge | E | Physical / property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Assign 3rd party certified & competent crane operator | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Overturning of crane during lifting after bypassing the load capacity or boom radius | E | Physical / Property | 3 | 4 | 12 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Check crane safety device including overload limiter and limit switch 3) Prepare lifting plan for critical lifting activity 4) Assign 3rd party certified & competent crane operator | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Material fall when round sling was cut after being in contact with the sharp edge of material being lifted | E | Physical / Property | 2 | 4 | 8 | C | 1)Check the lifting gears to be used before any lifting activity 2) Provide softener or pipe sleeve in areas where round sling is in contact with the sharp edge of the load 3) Lift using the lifting lugs provided 4) Barricade the lifting area and prohibit entry during lifting activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Material fall during lifting after using damaged lifting tackles (shackles) | E | Physical / Property | 3 | 4 | 12 | B | 1) Inspect all lifting tackles (shackles) to be used before the lifting activity start, inspection certificate 2) Prohibit anybody from entering the lifting area 3) Conduct high risk work last minute risk assessment 4) Assign 3rd party certified & competent rigger level 1 | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Material fall due to poor coordination between rigger and crane operator | E | Physical / Property | 3 | 4 | 12 | B | 1) Inspect the equipment & its documents and provide peration permit if permitted to work 2) Prepare lifting plan for critical lifting activity 3) Assign 3rd party certified & competent crane operator and rigger 4) Assign ONLY 1 rigger that will give signal to the crane operator 5) Conduct TBT prior to start of activity to discuss hazard of the job | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Material fall when lifting gears is detached from the hook block due to absence of safety latch | E | Physical / Property | 1 | 4 | 4 | D | 1) Check equipment using the daily equipment checklist before use 2) Check the safety latch of the main hook block to be in good working condition 3) High-risk work safety pre-qualification inspection 4) Barricade and strictly control personnel from entering the area | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Material fall due to loosened crane wire rope caused by improper revving | E | Physical / Property | 1 | 4 | 4 | D | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Check and inspect the equipment daily using the equipment checklist before use 3) Check crane safety device (limit switch, overload limit switch, crane monitor, etc) 4) Assign 3rd party certified & competent crane operator | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Material fall or personnel strike by load due to uncontrolled lowering of load | E | Physical / Property | 1 | 4 | 4 | D | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the equipment daily using the equipment checklist before use 3) Check crane safety device (limit switch, overload limit switch, crane monitor, etc) 4) Assign 3rd party certified & competent crane operator | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Material fall or personnel strike by load when lifting during strong wind | E | Physical / Property | 3 | 4 | 12 | B | 1) Strictly monitor the weather condition (wind condition), suspend lifting during strong winds 2) Follow lifting restriction depending on wind speed | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Personnel strike or hit by material during lifting due to absence of flagman | E | Physical / Property | 1 | 4 | 4 | D | 1) Assign trained flagman and provide megaphone to be used during high risk lifting activity 2) Restrict entry of personnel inside lifting area 3) Provide barricade & signage along the perimeter of lifting area | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Personnel hit or strike by load due to uncontrolled lifting / absence of tagline or guide rope | E | Physical / Property | 3 | 4 | 12 | B | 1) Assign competent worker to assist in lifting activity, holding the tag line or guide rope 2) Use minimum of 2-16mm diameter pp rope at least 20 meters in length or more as guide rope 3) Use megaphone or whistle to control people in the vicinity during the lifting activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Bending of crane boom while lifting heavy materials due to failure or not providing overload limit switch | E | Property | 3 | 4 | 12 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Check and inspect the equipment daily using the equipment checklist before use 3) Check crane safety device (limit switch, overload limit switch, crane monitor, etc) 4) Assign 3rd party certified & competent crane operator | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Absence of barricade along the crane working radius injuring other personnel when the material accidentally falls | E | Physical / Property | 2 | 5 | 10 | B | 1) Provide barricade & signage along the perimeter of the crane working radius 2) Assign trained flagman 3) Strictly supervise lifting activity 4) Conduct LMRA before starting any high risk lifting activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting and Installation of Transformer | Personnel fall while removing the lifting gears from the lifting lug due to absence of proper access / working platform | E | Physical | 3 | 4 | 12 | B | 1) Provide appropriate length of step / straight ladder to be sued when removing the shackles from the lifting lug 2) Worker to wear and use full body harness 3) Assign helpers to hold the ladder in place 4) Follow safe guidelines for ladder use | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Shifting of panel using forklift | Material fall caused by improper / unsafe handling of material while using forklift | E | Physical / Property | 3 | 4 | 12 | B | 1) Check safe lifting requirement for materials based on its weight 2) Check safety condition of equipment before use | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Shifting of panel using forklift | Overturning of forklift due to bad ground condition | E | Physical / Property | 3 | 3 | 9 | C | 1) Flat and smooth ground 2) Potholes, uneven surface immediately covered | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Shifting of panel using forklift | Overturning / tumbling of load due to sudden stopping of forklift | E | Physical / Property | 3 | 4 | 12 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Check forklift safety condition before starting work 3) Assign 3rd party certified & competent forklift operator | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Shifting of panel using forklift | Overturning of load due to unbalanced loading on the forklift forks | E | Physical / Property | 3 | 4 | 12 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Check forklift safety condition before starting work 3) Check weight of material to be carried before using the equipment 4) Assign 3rd party certified & competent forklift operator | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Shifting of panel using forklift | Forklift hitting existing structure due to absence of flagman | E | Property | 3 | 3 | 9 | C | 1) Assign trained flagman when to assis forklift when shifting materials at site 2) Conduct TBT prior to start of activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Shifting of panel using forklift | Forklift hitting flagman due to operators vision obstructed by load | E | Property | 3 | 4 | 12 | B | 1) Assign trained flagman when to assis forklift when shifting materials at site 2) Conduct TBT prior to start of activity 3) Flagman to keep away at least 5 meters from the equipment | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Overturning of crane after setting too close to excavation edge | E | Physical / property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Check the ground settlement of outrigger support during setting-up of mobile crane 4) Set outriggers at least 2 meters from the edge of excavation area 5) Assign 3rd party certified & competent crane operator | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Overturning of mobile crane due to ground settlement of out-rigger's support during lifting | E | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the ground condition, provide steel plate on unstable or backfilled area 2) Check the ground settlement of outrigger support during setting-up of mobile crane 3) Barricade the lifting area and prohibit entry of unwanted personnel | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Overturning / tumbling of mobile crane due to collapse of outrigger after failing to install the outrigger locking pins | E | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the ground condition, provide steel plate on unstable or backfilled area 2) Check and ensure outrigger locking pins are placed | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Overturning / tumbling of mobile crane due to failure to fully extend the crane outriggers | E | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the equipment daily using the equipment checklist 2) Check outriggers are fully extended and locking pins are engaged | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Overturning / tumbling of mobile crane due to equipment tyres not elevated and outrigger not properly set | E | Physical / Property | 2 | 4 | 8 | C | 1) Check & inspect set-up of crane before start of lifting activity, tyres of mobile crane elevated at least 1 inch from the ground | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Overturning of crane during lifting after bypassing the load capacity or boom radius | E | Physical / Property | 3 | 4 | 12 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Check crane safety device including overload limiter and limit switch 3) Assign 3rd party certified & competent crane operator | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Material fall when web sling was cut after being in contact with the sharp edge of material being lifted | E | Physical / Property | 2 | 4 | 8 | C | 1)Check the lifting gears to be used before any lifting activity 2) Provide softener or pipe sleeve in areas where web sling is in contact with the sharp edge of the load 3) Lift using the lifting lugs provided 4) Barricade the lifting area and prohibit entry during lifting activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Material fall during lifting after using damaged lifting tackles (shackles) | E | Physical / Property | 3 | 4 | 12 | B | 1) Inspect all lifting tackles (shackles) to be used before the lifting activity start, inspection certificate 2) Prohibit anybody from entering the lifting area 3) Assign 3rd party certified & competent rigger | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Material fall due to breaking of web sling during lifting | E | Physical / Property | 3 | 4 | 12 | B | 1) Inspect all web slings to be used before the lifting activity start 2) Check SWL of lifting gears compared to the material to be lifted 3) Assign 3rd party certified & competent rigger | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Material fall when lifting gears is detached from the hook block due to absence of safety latch | E | Physical / Property | 1 | 4 | 4 | D | 1) Check equipment using the daily equipment checklist before use 2) Check the safety latch of the main hook block to be in good working condition 3) Barricade and control personnel from entering the lifting area | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Material fall due to loosened crane wire rope caused by improper / loosened revving | E | Physical / Property | 1 | 4 | 4 | D | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Check and inspect the equipment daily using the equipment checklist before use 3) Check crane safety device (limit switch, overload limit switch, crane monitor, etc) 4) Assign 3rd party certified & competent crane operator | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Material fall or personnel strike by load when lifting during strong wind | E | Physical / Property | 3 | 4 | 12 | B | 1) Strictly monitor the weather condition (wind condition), suspend lifting during strong winds 2) Follow lifting restriction depending on wind speed | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Personnel strike or hit by material during lifting due to absence of flagman | E | Physical / Property | 1 | 4 | 4 | D | 1) Assign trained flagman and provide megaphone to be used lifting activity 2) Restrict entry of personnel inside the lifting area by providing barricade & signage along the perimeter of the lifting area | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Personnel hit or strike by load due to uncontrolled lifting / absence of tagline or guide rope | E | Physical / Property | 3 | 4 | 12 | B | 1) Assign workers to assist in holding the tag line or guide rope 2) Use minimum of 2-16mm diameter pp rope at least 10 meters in length or more as guide rope 3) Use megaphone or whistle to control people in the vicinity during lifting activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Lifting & Shifting of Electrical Panel | Absence of barricade along the crane working radius injuring other personnel when the material accidentally falls | E | Physical / Property | 2 | 5 | 10 | B | 1) Provide barricade & signage along the perimeter of the crane working radius 2) Assign trained flagman and strictly supervise lifting activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false |  | Head injury from head bump and not wearing safety helmet | E | Physical | 3 | 5 | 15 | B | 1) Wear safety helmet with chin strap properly 2) Post head bump signage and protective cushion | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Fall on the same level due to poor management of cables / poor housekeeping | E | Physical | 2 | 5 | 10 | B | 1) Conduct regular housekeeping and remove waste / unwanted materials immediately 2) Arrange electrical cable by hanging overhead using insulated S-bar or cable posts | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Fingers and hand injury due to absence of appropriate safety gloves after getting in contact with pointed edge of cable wire | E | Physical | 3 | 3 | 9 | C | 1) Wear appropriate safety hand gloves for the activity 2) Exercise caution and conduct TBt to discuss hazard related to activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Fingers and hand injury due to carelessness when using crimping tools | E | Physical | 2 | 2 | 4 | D | 1) Wear appropriate safety hand gloves for the activity 2) Exercise caution and conduct TBt to discuss hazard related to activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Fingers and hand injury caused by using damage / defective hand tools | E | Physical | 3 | 3 | 9 | C | 1) Check and inspect condition of hand tools before use 2) Wear appropriate PPE in relation to the activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Finger / hand injury caused when using sharp blades during cable dressing | E | Physical | 3 | 3 | 9 | C | 1) Wear appropriate safety hand gloves for the activity 2) Exercise caution and conduct TBt to discuss hazard related to activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Material damage after cable is repeatedly trampled | E | Property | 2 | 2 | 4 | D | 1) Secure cable to be terminate and provide cover if necessary 2) Provide barricade around the cable to be terminated | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Health injury caused by no wearing appropriate mask and regularly inhaling fiber optic shards | E | Health | 3 | 4 | 12 | B | 1) Conduct TBT to discuss hazard related to the activity 2) Exercise caution and assign enough personnel for the activity 3) Provide appropriate PPE, hand gloves / face mask, aside from the other minimum required PPE | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Fire / explosion when using defective gas torch used for heat shrinking of insulator / tubing | E | Physical / Property | 3 | 3 | 9 | C | 1) Check / inspect blow torch to be used for signs of defect 2) Use butane powered torch and put off fire when not in use 3) Assign fire watchman equipped with fire extinguisher | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Fire / burn due to improper use of gas torch | E | Physical | 2 | 4 | 8 | C | 1) Check / inspect blow torch to be used for signs of defect 2) Use butane powered torch and put off fire when not in use 3) Assign fire watchman equipped with fire extinguisher | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Heat stress / exhaustion caused by working under the sun | E | Physical / Health | 3 | 4 | 12 | B | 1) Provide temporary rest shelter near the work area 2) Ensure supply of cool drinking water and ventilation fan to workers 3) Provide frequent breaks and avoid working between 12:00 ~ 15:00 Hrs. during the summer season | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
false | Cable termination, dressing and tagging | Back / hand pain due to repititive movement | E | Physical | 3 | 3 | 9 | C | 1) Lift materials less than 25 kilos 2) provide regular rest breaks to disrupt monotony of movement 3) Assign enough personnel for the activity | sungil Heo | 2024-01-31 | 1 | 1 | 1 | E |  | SWRO 전기작업표준 (플랜트).xls | Sheet1
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | EHS | E
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | EHS | H
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | EHS | S
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 빈도 Risk Rate | 1
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 빈도 Risk Rate | 2
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 빈도 Risk Rate | 3
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 빈도 Risk Rate | 4
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 빈도 Risk Rate | 5
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 강도 Severity | 1
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 강도 Severity | 2
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 강도 Severity | 3
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 강도 Severity | 4
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 강도 Severity | 5
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 빈도 Likelihood | 1
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 빈도 Likelihood | 2
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 빈도 Likelihood | 3
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 빈도 Likelihood | 4
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 빈도 Likelihood | 5
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 강도 Severity | 1
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 강도 Severity | 2
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 강도 Severity | 3
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 강도 Severity | 4
[17 empty] | SWRO 전기작업표준 (플랜트).xls | 코드목록 | 강도 Severity | 5