## Sheet1
삭제 Del | 작업활동 및 내용 Work & Contents | 유해위험요인 및 환경측면 영향 Hazard & Risk | EHS | 피해형태 및 환경영향 Damage & Effect | 위험성 Risk Rate | 위험성 Risk Rate.1 | 위험성 Risk Rate.2 | 등급 Rate | 개선대책 및 세부관리방안 Corrective Action | 개선담당자 Responsibility | 개선일자 Action Date | 위험성 Risk Rate | 위험성 Risk Rate.1 | 위험성 Risk Rate.2 | 등급 Rate
삭제 Del | 작업활동 및 내용 Work & Contents | 유해위험요인 및 환경측면 영향 Hazard & Risk | EHS | 피해형태 및 환경영향 Damage & Effect | 빈도 Risk Rate | 강도 Severity | T | 등급 Rate | 개선대책 및 세부관리방안 Corrective Action | 개선담당자 Responsibility | 개선일자 Action Date | 빈도 Likelihood | 강도 Severity | T | 등급 Rate
false | Transport / Delivery of concrete blocks materials to site | Collision between transport vehicle with other site vehicle due to absence of flagman | S | Physical / Property | 3 | 5 | 15 | B | 1) Conduct safety check before use of construction vehicles. 2) Install safety device for construction vehicle and place the signal man. 3) All vehicles and heavy vehicles shall engaged hazard lights while travelling inside the plant. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of concrete blocks materials to site | Collision between transport vehicle with existing site structure due to overspeeding / non observance of traffic rules | S | Property | 3 | 4 | 12 | B | 1) Vehicle follow 20 kph speed limit 2) Vehicle pass at designated road 3) Implemented disciplinary action for violators. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of concrete blocks materials to site | Site personnel struck by transport vehicle | S | Physical | 2 | 5 | 10 | B | 1) Provide pedestrian acecss for site personnel 2) Wear personal protective equipment (visibility vest) | Dongil Lee | 2024-01-27 | 1 | 1 | 1 | E
false | Transport / Delivery of concrete blocks materials to site | Overturning of transport vehicle caused by bad ground condition | S | Property | 3 | 3 | 9 | C | 1) Flat and smooth ground 2) Potholes, uneven surface immediately covered | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of concrete blocks materials to site | Material fall due to absence of trailer bed railing | S | Property | 2 | 3 | 6 | C | 1) Check safety rails of trailer bed. 2) Use steel railings and not wood / timber railings | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of concrete blocks materials to site | Material fall caused by improper / unsafe stacking | S | Property | 2 | 3 | 6 | C | 1) Keep materials separately, Don't pile more than 1.5m 2) Keep materials on top of wood pallet and secured | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of concrete blocks materials to site | Material fall due to unsecured load and no proper lashing | S | Property | 2 | 5 | 10 | B | 1) Concrete blocks materials placed on wood pallet and tied properly 2) Materials secured with lashing belt | Dongil Lee |  | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Overturning of forklift due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Remove unwanted materials that obstruct the pathway or working area of forklift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Overturning of forklift due to unbalanced lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Exercise caution when shifting concrete blocks placed on wood pallet and make sure they are secured properly 2) Conduct test lift to ensure center of gravity of load is between the forks of equipment | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Overturning of forklift due to heavy load being lifted | S | Physical / Property | 3 | 5 | 15 | B | 1) Check weight of bundle of concrete blocks from material delivery receipt 2) Check capacity of forklift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Overturning of forklift due to defective equipment during material shifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check forklift control / safety device if properly working 2) Check stability and forklift condition before use 3) Operator shall conduct daily inspection using equipment checklist before operations. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Fall of load due to short forks | S | Property | 3 | 5 | 15 | B | 1) check dimension of materials to be lifted 2) Check if forks of equipment extend at least 12 inches from the material being lifted | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Fall of load from trailer after being pushed by forks of forklift | S | Property | 3 | 5 | 15 | B | 1) Assign banks man and no person must be allowed on the other side of the trailer bed 2) Assign qualified helper to assist forklift operator when inserting the forks of the forklift. 3) Ensure operator's competency by verifying certificates. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Fall of load due to multiple lifting | S | Property | 3 | 5 | 15 | B | 1) Do not lift multiple materials that is not secured together 2) Do not lift pallet with concrete blocks that is not properly tied together. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Personnel / flagman struck by forks or equipment or load being lifted / shifted | S | Physical | 3 | 5 | 15 | B | 1) Maintain minimum of 5 meter distance from the equipment 2) Use flag and whistle to give signal to the forklift operator 3) Stop equipment if other workers are nearby | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Forklift hitting other steel structure materials stored at temporary laydown area | S | Property | 3 | 5 | 15 | B | 1) Forklift to operate at 5~10kph when shifting materials 2) Use flag and whistle to give signal to the forklift operator | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Fall of load when shifting and lifting too high | S | Property | 3 | 5 | 15 | B | 1) Lower the load as close to the ground before manoeuvering 2) Do not lift load beyond the forklift capacity | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of concrete / CMU block materials using forklift at work site area | Fall of load while shifting materials on a reverse direction | S | Property | 3 | 5 | 15 | B | 1) Avoid shifting materials on a reverse manner 2) Place the load to the ground and shift forklift direction so that it will be transported in a forward direction | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of concrete / CMU blocks | Overturning of crane due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Use steel plate over backfilled / uneven area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of concrete / CMU blocks | Overturning of crane due to improper set-up | S | Physical / Property | 3 | 5 | 15 | B | 1) Set-up crane outrigger minimum of 2 meters from excavation 2) Crane balance and wheels not touching the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of concrete / CMU blocks | Overturning of crane due to failed outrigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Outrigger must be fully extended without hydraulic leak 2) Outirigger locking pin installed 3. Outrigger pads in good condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of concrete / CMU blocks | Overturning of crane due to defective equipment during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check crane control / safety device if properly working 2) Check stability and crane condition before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of concrete / CMU blocks | Fall of load by lifting blocks from wood pallet | S | Physical / Property | 3 | 5 | 15 | B | 1) Use material basket to lift concrete blocks in bulk quantity 2) Check 3rd party inspection certificate of material basket 3) Avoid lifting concrete blocks placed on wood pallet or wood box | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of concrete / CMU blocks | Fall of load due to unsafe slinging | S | Property | 3 | 5 | 15 | B | 1) Use proper slinging when lifting material box 2) Use designated lifting lugs if available 3) Avoid lifting concrete blocks using improvised lifting gear | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of concrete / CMU blocks | Fall of load due to bad weather condition | S | Property | 3 | 5 | 15 | B | 1) No lifting if wind speed more than 10m/s or 36kph 2) No lifting during heavy rain, sand storm or foggy condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of concrete / CMU blocks | Fall of load due to improper signalling | S | Property | 3 | 5 | 15 | B | 1) Only assigned 3rd party certified rigger to give signal 2) Use radio or additional rigger in case of blind spot | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of concrete / CMU blocks | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Barricade perimeter of crane lifting radius 3) No personnel allowed under the load or crane boom 4) Avoid lifting the material over head | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of concrete / CMU blocks | Hitting other structure by load during lifting | S | Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of concrete / CMU blocks | Using uninspected power tools | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect and check power tools before using 2) Check if machine guarding and auxiliary handle available | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of concrete / CMU blocks | Using power tools with frayed / damage extension cable | S | Physical / Property | 3 | 5 | 15 | B | 1) Check power tools extension cable for posssible damage / defect 2) Inspect cable connection to the power tool and male socket | Dongil Lee |  | 1 | 1 | 1 | E
false | Cutting of concrete / CMU blocks | Electric shock caused by inadequate insulation and absence of ELCB | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect if cable is 3-phase or double insulated 2) Check power source if provided with 30mA ELCB 3) Inspect if electrical DB is properly grounded | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of concrete / CMU blocks | Hand injury due to improper use of angle grinder | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if personnel is competent to use the angle grinder 2) Check proper handling and use of power tools by worker | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of concrete / CMU blocks | Shattering of cutting disk due to low RPM / using defective disk | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect if cutting disk RPM is higher than the power tools rated RPM 2) Inspect if disk has defect, crack or dull sound and remove immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of concrete / CMU blocks | Dust generated during cutting of concrete blocks | S | Physical | 3 | 5 | 15 | B | 1) Avoid cutting of concrete blocks inside the building room 2) Utilize exhaust fan if unavoidable to dissipate dust generated | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of concrete / CMU blocks | Eye / face injury from flying splinters / concrete blocks particles | S | Property | 3 | 5 | 15 | B | 1) Wear and use full face shield aside from safety glasses 2) Use blocking to prevent concrete blocks particles from spreading | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of concrete / CMU blocks | Fall on the same level due to poor management of cables / poor housekeeping | S | Physical | 3 | 5 | 15 | B | 1) Conduct regular housekeeping and remove waste / unwanted materials 2) Arrange electrical cable by hanging overhead using insulated S-bar or cable posts | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of concrete mortar | Hand / arm injury after being caught on the rotating drum | S | Physical / Property | 3 | 5 | 15 | B | 1) Use bucket or other small container to fill the drum with material 2) Drum should be in angled position for ease in placing materials 3) Lower the revolution of the drum during material filling | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of concrete mortar | Eye / face injury from flying concrete mixture | S | Physical / Property | 3 | 5 | 15 | B | 1) Wear and use full face shield aside from safety glasses 2) Drum should be on upright position when mixing commence | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of concrete mortar | Skin problem from contact with mortar | S | Physical / Property | 3 | 5 | 15 | B | 1) Wear long sleeved clothing and hand gloves to cover exposed skin 2) Wear disposable cover-all as additional precaution | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of concrete mortar | Entanglement with rotating drum due to wearing loose clothing | S | Physical / Property | 3 | 5 | 15 | B | 1) Ensure clothes are properly tucked in into pants 2) Avoid wearing traditional dress with long shirt | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of concrete mortar | Health problem when inhaling cement fumes | S | Physical / Property | 3 | 5 | 15 | B | 1) Wear and use dust mask when handling cement 2) Ensure water is inside the drum before cement is place to minimize dust | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Personnel fall from scaffold due to unstable platform | S | Physical | 3 | 5 | 15 | B | 1) Secure wood planks with board clamp and wear saefty harness 2) Install auxiliary lifeline and use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Fall due to insufficient working platform | S | Physical | 3 | 5 | 15 | B | 1) Install the missing wood planks of the scaffold platform 2) Wear full body harness and use 3) Install auxiliary lifeline and use 4) Scaffold modification shall not be performed by anyone other than the scaffolder. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Personnel fall caused by not wearing safety harness | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lifeline 2) Comply with 100% tie-off 3) Before height work, practice double hook demonstration 4) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Head injury from head bump and not wearing safety helmet | S | Physical | 3 | 5 | 15 | B | 1) Wear safety helmet with chin strap properly 2) Post head bump signage and protective cushion | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Overturning due to bad condition of scaffold structure | S | Physical | 3 | 5 | 15 | B | 1) Scaffold Inspector to inspect the scaffold structure before use 2) Wear and use full body harness | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Hand tools dropped while working on elevated area | S | Physical / Property | 3 | 4 | 12 | B | 1) Secure all hand tools with PP rope and tie on safety harness or hand 2) Remove hand tools left unattended | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Fall from ladder while carrying tools / wood materials | S | Physical / Property | 3 | 4 | 12 | B | 1) Maintain 3-point contact when climbing a ladder 2) Do not carry tools / materials by hand when climbing the ladder 3) Use belt bags to strap hand tools | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Fall of concrete blocks due to insufficient platform / collapse of platform | S | Physical / Property | 3 | 4 | 12 | B | 1) Avoid stacking / storing excessive number of concrete blocks 2) Check if platform is properly planked and clamped 3, Avoid to keep blocks above the Toe board. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Fall of materials due to absence of toe board | S | Property | 3 | 4 | 12 | B | 1) Install toe board on all edge of the working platform 2) Do not stack materials above the height of the toe board | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Fall of materials due to overstacking | S | Property | 3 | 4 | 12 | B | 1) Do not stack materials above the height of the toe board 2) Stack materials on the wall side of the working platform | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Fall of materials due to carelessness in material handling | S | Physical | 3 | 4 | 12 | B | 1) Wear and use proper hand gloves when handling concrete blocks 2) Use mechanical pallet jack or other lifting device 3) Minimize passing of concrete blocks by hand | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of Concrete / CMU blocks | Fall of Block materials due to moving of block with pallet trolley | S | Physical | 3 | 4 | 12 | B | 1 , While transporting the block in the pallet trolley the numbers of block/Method of stacking should be checked and this should not be excessive. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material / Manual handling at the site | Material fall due to damage pail handle | S | Physical | 3 | 4 | 12 | B | 1) Check paint handle before lifting / shifting 2) Ensure to follow MSDS Guidelines on the storage, Handling and Use of paint materials, Provision of safe temporary ventilated designed paint storage area. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material / Manual handling at the site | Material fall due to unsafe passing | S | Property | 3 | 4 | 12 | B | 1) Personnel to wear proper PPE, leather or rubber coated hand gloves 2) Avoid throwing materials and pass by hand only | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material / Manual handling at the site | Fall on the same floor due to scattered materials | S | Physical | 3 | 3 | 9 | C | 1) Conduct housekeeping and remove loose materials from the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material / Manual handling at the site | Back / hand pain due to repititive movement | S | Physical | 3 | 3 | 9 | C | 1) Lift materials less than 25 kilos 2) provide breaks to break monotony of movement | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of paint | Electric shock caused by inadequate insulation and absence of ELCB | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect if cable is 3-phase or double insulated 2) Check power source if provided with 30mA ELCB 3) Inspect if electrical DB is properly grounded | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of paint | Eye splash of chemical during mixing | S | Physical | 1 | 4 | 4 | D | 1) Follow instructions based on MSDS 2) Wear Personal protective equipment / full face shield 3) Provide emergency eye wash at the work area 4) Hazmat Trained workers shall be assigned for Painting Activity. 5) Provide Proper / Appropriate PPE For the painting activity as per the requirement from MSDS Of Paint and Regularly Inspect them before each Use. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of paint | Caught in / entanglement because of carelessness in use of handheld electric mixer during the mixing of paint | S | Physical | 2 | 3 | 6 | C | 1) Exercise caution and avoid wearing loose clothing / safety gloves when using the handheld electric mixer | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of paint | Personnel accidentally drinking thinner placed on unmarked bottle | S | Physical / Health | 3 | 4 | 12 | B | 1) Manage storage of HAZMAT at the work site 2) Comply standard for temporary HAZMAT bottle 3) Provide GHS marking and label on all temporary HAZMAT container | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of paint | Fire / explosion due to absence of proper temporary storage area at site | S | Environmental / Property | 3 | 4 | 12 | B | 1) Provide proper temporary storage for dangerous (HAZMAT) material and avoid storing them in confined space area or under direct sunlight or near hot works areas 2) Provide fire extinguisher and emergency spill kit | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of paint | Fall on the same floor due to scattered materials | S | Physical | 3 | 3 | 9 | C | 1) Conduct housekeeping and remove loose materials from the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of paint | Soil pollution after HAZMAT spillage due to absence of secondary containment at temporary storage area | S | Environmental / Property | 3 | 4 | 12 | B | 1) Provide secondary containment or drip tray at HAZMAT storage area 2) Provide emergency spill kit and manage properly | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of paint | Soil pollution after spilling of paint during mixing | S | Environmental / Property | 2 | 4 | 8 | C | 1) Ensure paint bucket cover is replaced tightly when not in use 2) Provide secondary containment / drip tray and emergency spill kit | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Fall on the same level due to poor management of cables / poor housekeeping | S | Physical | 2 | 5 | 10 | B | 1) Conduct regular housekeeping and remove waste / unwanted materials 2) Arrange electrical cable by hanging overhead using insulated S-bar or cable posts | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Suffocation due to absence of safety mask while applying paint putty | S | Physical | 3 | 4 | 12 | B | 1) Provide appropriate safety mask for the users or workers 2) Provide ventilation fan when working in confined space area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Suffocation due to oxygen deficiency while working in confined space area | S | Physical | 2 | 4 | 8 | C | 1) Check oxygen level before start of any activity inside confined space 2) Provide enough exhaust / ventilation fan for confined space work | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Fall because of absence of cover at openings | S | Physical | 3 | 4 | 12 | B | 1) Install cover on all floor opening and safety guard to prevent falling 2) Provide appropriate safety / warning signage | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Personnel fall because of using damaged ladder | S | Physical | 3 | 4 | 12 | B | 1) Avoid using straight ladder as working platform and made of wood 2) use step / A-type ladder of approved materials 3) Check step ladder condition before use and assign worker to hold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Personnel fall from ladder scaffold and mobile ladder | S | Physical | 3 | 3 | 9 | C | 1) Check the condition of the access ladder 2) Install the appropriate access ladder for the mobile scaffold 3) Working platform fully planked and opening covered | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Damage to the eye because of absence of safety goggles | S | Physical | 1 | 4 | 4 | D | 1) Wear appropriate safety goggles / full face shield | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Tumbling and collision between worker due to insufficient lighting | S | Physical | 2 | 3 | 6 | C | 1) Provide enough lighting with more than 60 Lux illumination at the work site | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Fall caused by unsafe condition of locking and strength of mobile scaffold | S | Physical | 3 | 2 | 6 | C | 1) Fix platform tightly on mobile scaffold 2) Wear and use full body harness 3) Check lock of caster wheels are engaged | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Overturning due to bad condition of scaffold structure | S | Physical | 3 | 5 | 15 | B | 1) Scaffold Inspector to inspect the scaffold structure before use 2) Wear and use full body harness | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Fall from mobile scaffold when moved while working | S | Physical | 3 | 2 | 6 | C | 1) Do not move mobile scaffold while personnel are working or on top of the mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Personnel fall due to absence of appropriate access ladder | S | Physical | 3 | 2 | 6 | C | 1) Install the necessary access ladder leading to the working platform of the mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Personnel fall caused by not wearing safety harness | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Comply with 100% tie-off 3) Before height work, practice double hook demonstration 4) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Personnel fall due to absence of safety rail and safety belt | S | Physical | 3 | 2 | 6 | C | 1) Install standard height guard rail / safety rail on all sides 2) Wear and use full body harness when working on mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Overturning / personnel fall due to sudden movement of mobile scaffold for failure to lock caster wheels | S | Physical / Property | 3 | 3 | 9 | C | 1) Check safety condition of mobile scaffold before use 2) Inspect and check if caster wheels of mobile scaffold are locked | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Fall from ladder while carrying tools / materials | S | Physical / Property | 2 | 4 | 8 | C | 1) Maintain 3-point contact when climbing a ladder 2) Do not carry tools / materials by hand when climbing the ladder 3) Use belt bags to strap hand tools | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Material fall because because of absence of toe board on mobile scaffold | S | Physical / Property | 2 | 2 | 4 | D | 1) Install toe board on all platform edges 2) Install additional safety net if practicable | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Overturning due to absence of adequate support for mobile scaffold | S | Physical / Property | 3 | 2 | 6 | C | 1) Install the necessary diagonal bracing support for the mobile scaffold 2) Install plan bracing to prevent twisting of mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Overturning due of absence of outrigger on mobile scaffold | S | Physical / Property | 3 | 1 | 3 | D | 1) Install appropriate ourigger supprot to prevent overturning 2) Install safety alarm device for overturning | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Application of paint putty | Skin rashes when workers use thinner for washing / removing paint from their body | S | Physical / Health | 3 | 4 | 12 | B | 1) Provide fresh water & soap at the work area 2) Strictly control issuance and use of thinner 3) Educate painters on the hazard associated with unsafe use of HAZMAT 4) Provide disposable cover-all for painters | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Electric shock caused by inadequate insulation and absence of ELCB | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect if cable is 3-phase or double insulated 2) Check power source if provided with 30mA ELCB 3) Inspect if electrical DB is properly grounded | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Fall on the same level due to poor management of cables / poor housekeeping | S | Physical | 3 | 5 | 15 | B | 1) Conduct regular housekeeping and remove waste / unwanted materials 2) Arrange electrical cable by hanging overhead using insulated S-bar or cable posts | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Suffocation due to absence of safety mask while applying paint | S | Physical | 3 | 4 | 12 | B | 1) Provide appropriate safety mask for the users or workers 2) Provide ventilation fan when working in confined space area 3) Provide proper / appropriate PPE for the painting activity as per the requirement from MSDS of paint and regularly inspect them before each use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Suffocation due to oxygen deficiency while working in confined space area | S | Physical | 2 | 4 | 8 | C | 1) Check oxygen level before start of any activity inside confined space 2) Provide enough exhaust / ventilation fan for confined space work | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Fire / explosion due to improper / unsafe use of flammable materials | S | Physical / Property | 3 | 5 | 15 | B | 1) Check MSDS for proper handling of HAZMAT 2) Wear proper PPE and provide fire extinguisher | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Fire / explosion due to improper / unsafe storage of flammable / explosive materials | S | Physical / Property | 3 | 5 | 15 | B | 1) Store materials on proper temporary HAZMAT storage area, follow MSDS requirement and Doosan HAZMAT storage guideline 2) Provide proper lock, barricade / cage, safety / warning signage, information of responsible person, emergency eye wash, fire extinguisher, etc. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Fall because of absence of cover at openings | S | Physical | 3 | 4 | 12 | B | 1) Install cover on all floor opening and safety guard to prevent falling 2) Provide appropriate safety / warning signage | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Personnel fall because of using damaged ladder | S | Physical | 3 | 4 | 12 | B | 1) Avoid using straight ladder as working platform and made of wood 2) use step / A-type ladder of approved materials 3) Check step ladder condition before use and assign worker to hold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Electric shock due to absence of proper grounding / earthing | S | Physical | 3 | 4 | 12 | B | 1) Install copper grounding rod and connect body grounding of distribution board properly 2) Check resistance of copper grounding and must be below 5 ohms | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Electric shock caused by inadequate insulation and absence of ELCB | S | Physical | 3 | 4 | 12 | B | 1) Inspect if cable is 3-phase or double insulated 2) Check power source if provided with 30mA ELCB 3) Inspect if electrical DB is properly grounded | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Electric shock caused by using damage / frayed electric wire | S | Physical | 3 | 4 | 12 | B | 1) Check if electric / extension cable is 3-phase or double insulated 2) Check electric / extension cable for damage, frayed or defect | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Electric shock because of misconduct in the safety check for electric wire | S | Physical / Property | 2 | 4 | 8 | C | 1) Check electrical / extension cable before use 2) Check connection of electrical wire to plug / socket outlet | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Personnel fall from ladder scaffold and mobile ladder | S | Physical | 3 | 3 | 9 | C | 1) Check the condition of the access ladder 2) Install the appropriate access ladder for the mobile scaffold 3) Working platform fully planked and opening covered | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Damage to the eye because of absence of safety goggles | S | Physical | 1 | 4 | 4 | D | 1) Wear appropriate safety goggles / full face shield | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Tumbling and collision between worker due to insufficient lighting | S | Physical | 2 | 3 | 6 | C | 1) Provide enough lighting with more than 60 Lux illumination at the work site | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Electric shock because the electric wires are exposed to water | S | Physical | 2 | 3 | 6 | C | 1) Check electrical cable condition and plug / socket conenction 2) Provide 30mA ELCB for the socket outlet of distribution board | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Fall caused by unsafe condition of locking and strength of mobile scaffold | S | Physical | 3 | 2 | 6 | C | 1) Fix platform tightly on mobile scaffold 2) Wear and use full body harness 3) Check lock of caster wheels are engaged | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Overturning due to bad condition of scaffold structure | S | Physical | 3 | 5 | 15 | B | 1) Scaffold Inspector to inspect the scaffold structure before use 2) Wear and use full body harness | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Hand tools dropped while working on elevated area | S | Physical / Property | 3 | 4 | 12 | B | 1) Secure all hand tools with PP rope and tie on safety harness or hand 2) Remove hand tools left unattended | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Fall from mobile scaffold when moved while working | S | Physical | 3 | 2 | 6 | C | 1) Do not move mobile scaffold while personnel are working or on top of the mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Personnel fall due to absence of appropriate access ladder | S | Physical | 3 | 2 | 6 | C | 1) Install the necessary access ladder leading to the working platform of the mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Personnel fall caused by not wearing safety harness | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Comply with 100% tie-off 3) Before height work, practice double hook demonstration 4) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Personnel fall due to absence of safety rail and safety belt | S | Physical | 3 | 2 | 6 | C | 1) Install standard height guard rail / safety rail on all sides 2) Wear and use full body harness when working on mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Overturning / personnel fall due to sudden movement of mobile scaffold for failure to lock caster wheels | S | Physical / Property | 3 | 3 | 9 | C | 1) Check safety condition of mobile scaffold before use 2) Inspect and check if caster wheels of mobile scaffold are locked | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Fall from ladder while carrying tools / materials | S | Physical / Property | 3 | 4 | 12 | B | 1) Maintain 3-point contact when climbing a ladder 2) Do not carry tools / materials by hand when climbing the ladder 3) Use belt bags to strap hand tools | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Fall because because of absence of toe board on mobile scaffold | S | Physical / Property | 2 | 2 | 4 | D | 1) Install toe board on all platform edges 2) Install additional safety net if practicable | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Overturning due to absence of adequate support for mobile scaffold | S | Physical / Property | 3 | 2 | 6 | C | 1) Install the necessary diagonal bracing support for the mobile scaffold 2) Install plan bracing to prevent twisting of mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Paint application | Fall because of absence of outrigger on mobile scaffold | S | Physical / Property | 3 | 1 | 3 | D | 1) Install appropriate ourigger supprot to prevent overturning 2) Install safety alarm device for overturning | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Overturning of fork lift due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Remove unwanted materials that obstruct the pathway or working area of fork lift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Overturning of fork lift due to unbalanced lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Avoid lifting steel structure more than 6 meters in length 2) Conduct test lift to ensure center of gravity of load is between the forks of equipment | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Overturning of fork lift due to heavy load being lifted | S | Physical / Property | 3 | 5 | 15 | B | 1) Check weight of steel structure from material delivery receipt 2) Check capacity of fork lift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Overturning of fork lift due to defective equipment during material shifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check fork lift control / safety device if properly working 2) Check stability and fork lift condition before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Fall of load due to short forks | S | Property | 3 | 5 | 15 | B | 1) check dimension of materials to be lifted 2) Check if forks of equipment extend at least 12 inches from the material being lifted | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Fall of load from trailer after being pushed by forks of fork lift | S | Property | 3 | 5 | 15 | B | 1) Assign banks man and no person must be allowed on the other side of the trailer bed 2) Assign qualified helper to assist forklift operator when inserting the forks of the fork lift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Fall of load due to multiple lifting | S | Property | 3 | 5 | 15 | B | 1) Do not lift multiple steel materials that is not secured together 2) Do not lift materials of different dimension, weight and configuration | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Personnel / flagman struck by forks or equipment | S | Physical | 3 | 5 | 15 | B | 1) Maintain minimum of 5 meter distance from the equipment 2) Use flag and whistle to give signal to the fork lift operator 3) Stop equipment if other workers are nearby | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Fork lift hitting other steel structure materials stored at temporary laydown area | S | Property | 3 | 5 | 15 | B | 1) Forklift to operate at 5~10kph when shifting steel structure materials 2) Use flag and whistle to give signal to the fork lift operator | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Fall of load when shifting and lifting too high | S | Property | 3 | 5 | 15 | B | 1) Lower the load as close to the ground before manoeuvring 2) Do not lift load beyond the fork lift capacity | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of steel structure materials using forklift at temporary site storage area | Fall of load while shifting materials on a reverse direction | S | Property | 3 | 5 | 15 | B | 1) Avoid shifting materials on a reverse manner 2) Either place the load to the ground and shift fork lift direction so that it will be transported in a forward direction | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Overturning of crane due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Use steel plate over backfilled / uneven area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Overturning of crane due to improper set-up | S | Physical / Property | 3 | 5 | 15 | B | 1) Set-up crane outrigger minimum of 2 meters from excavation 2) Crane balance and wheels not touching the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Overturning of crane due to failed outrigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Outrigger must be fully extended without hydraulic leak 2) Outirigger locking pin installed 3) Outrigger pads in good condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Overturning of crane due to defective equipment during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check crane control / safety device if properly working 2) Check stability and crane condition before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Fall of load due to defective lifting gears | S | Physical / Property | 3 | 5 | 15 | B | 1) Check lifting gears before / after use 2) Remove damage / defective lifting gears immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Fall of load due to lifting unsecured materials | S | Property | 3 | 5 | 15 | B | 1) Lift only scaffold standard, ledger & transom if placed on racks 2) Avoid lifting materials placed on wood pallet or wood box | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Fall of load due to unsafe slinging | S | Property | 3 | 5 | 15 | B | 1) Use proper slinging & padding depending on the load 2) Use designated lifting lugs if available 3) Avoid lifting multiple materials of different configuration | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Fall of load due to bad weather condition | S | Property | 3 | 5 | 15 | B | 1) No lifting if wind speed more than 10m/s or 36kph 2) No lifting during heavy rain, sand storm or foggy condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Fall of load due to improper signalling | S | Property | 3 | 5 | 15 | B | 1) Only assign 3rd party certified rigger to give signal 2) Use radio or additional rigger in case of blind spot | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Barricade perimeter of crane lifting radius 3) No personnel allowed under the load or crane boom 4) Avoid lifting the material over head | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Hitting other structure by load during lifting | S | Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Fall of load due to unsafe use of wood support | S | Physical / Property | 3 | 5 | 15 | B | 1) Use similar size of timber materials and cris-cross when placed one over the other 2) Place support on even ground at equal interval | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Assembly of steel structure components | Hand injury due to improper use of hand tools | S | Physical | 3 | 4 | 12 | B | 1) Check hand and power tools to be used 2) Wear proper PPE especially hand gloves | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Overturning of crane / manlift due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Use steel plate over backfilled / uneven area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Overturning of crane due to improper set-up | S | Physical / Property | 3 | 5 | 15 | B | 1) Set-up crane outrigger minimum of 2 meters from excavation 2) Crane balance and wheels not touching the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Overturning of crane due to failed outrigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Outrigger must be fully extended without hydraulic leak 2) Outirigger locking pin installed 3. Outrigger pads in good condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Overturning of crane due to defective equipment during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check crane control / safety device if properly working 2) Check stability and crane condition before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Fall of load due to defective lifting gears | S | Physical / Property | 3 | 5 | 15 | B | 1) Check lifting gears before / after use 2) Remove damage / defective lifting gears immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Fall of load due to unsafe slinging | S | Property | 3 | 5 | 15 | B | 1) Use proper slinging & padding depending on the load 2) Use designated lifting lugs if available | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Fall of load due to bad weather condition | S | Property | 3 | 5 | 15 | B | 1) No lifting if wind speed more than 10m/s or 36kph 2) No lifting during heavy rain, sand storm or foggy condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Fall of load due to improper signalling / incompetent rigger | S | Property | 3 | 5 | 15 | B | 1) Assign 3rd party certified rigger to give signal 2) Use radio or additional rigger in case of blind spot | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Barricade perimeter of crane lifting radius 3) No personnel allowed under the load or crane boom 4) Avoid lifting the material over head 5) Use whistle / megaphone siren to warn other personnel in the area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Hitting other structure by load during lifting | S | Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Overturning of column due to absence of proper support | S | Physical / Property | 3 | 5 | 15 | B | 1) Provide a minimum or 3 guy wire made of wire rope as support for the column 2) Check quantity, positioning and manner of installing the wire clips of the guy wire | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Collapse of column due to damage shim padding / anchor bolts | S | Physical / Property | 3 | 4 | 12 | B | 1) Check the condition of the shim pads and anchor bolts for damage 2) Nuts for all anchor bolts must be installed and tightened manually | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Overturning of column due to untightened guy wire support | S | Physical / Property | 3 | 5 | 15 | B | 1) Use chain block to straighten the slack of the guy wire 2) Connect the guy wires on stable and firm anchorage / structure | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of steel structure (column) | Fall of personnel from manlift when removing the lifting gears | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Comply with 100% tie-off 3) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Overturning of crane / manlift due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Use steel plate over backfilled / uneven area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Overturning of crane due to improper set-up | S | Physical / Property | 3 | 5 | 15 | B | 1) Set-up crane outrigger minimum of 2 meters from excavation 2) Crane balance and wheels not touching the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Overturning of crane due to failed outrigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Outrigger must be fully extended without hydraulic leak 2) Outirigger locking pin installed 3) Outrigger pads in good condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Overturning of crane due to defective equipment during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check crane control / safety device if properly working 2) Check stability and crane condition before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Fall of load due to defective lifting gears | S | Physical / Property | 3 | 5 | 15 | B | 1) Check lifting gears before / after use 2) Remove damage / defective lifting gears immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Fall of load due to unsafe slinging | S | Physical / Property | 3 | 5 | 15 | B | 1) Use proper slinging & padding depending on the load 2) Use designated lifting lugs if available | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Fall of load due to improper signalling | S | Physical / Property | 3 | 4 | 12 | B | 1) Assign 3rd party certified rigger to give signal 2) Use radio or additional rigger in case of blind spot | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Personnel struck by load when lifting | S | Physical | 3 | 4 | 12 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Barricade perimeter of crane lifting radius 3) No personnel allowed under the load or crane boom 4) Use whistle / megaphone siren to warn other personnel in the area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Hitting other structure by load during lifting | S | Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Fall of personnel from manlift basket when installing the steel structural beams / bracing | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Provide a separate lifeline or web sling wrapped on installed steel component where they can tie-off their lanyards separately 3) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Fall of beam / bracing due to insufficient bolting and untightened nuts of bolts | S | Physical / Property | 3 | 4 | 12 | B | 1) Minimum of 60% of number of bolts must be connected for each joint 2) All bolts must be manually tightened fully using ratchet | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural beam / bracing | Fall of hand tools / nuts / bolts during bolting of steel structure | S | Physical / Property | 3 | 4 | 12 | B | 1) All bolts and nuts must be placed on bucket or container 2) Hand tools provided with restraining rope and tied to prevent fall | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Overturning of crane / manlift due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Use steel plate over backfilled / uneven area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Overturning of crane due to improper set-up | S | Physical / Property | 3 | 5 | 15 | B | 1) Crane balanced and wheels not touching the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Overturning of crane due to failed outrigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Outrigger must be fully extended without hydraulic leak 2) Outirigger locking pin installed 3) Outrigger pads in good condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Overturning of crane due to defective equipment during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check crane control / safety device if properly working 2) Check stability and crane condition before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Fall of load due to defective lifting gears | S | Physical / Property | 3 | 5 | 15 | B | 1) Check lifting gears before / after use 2) Remove damage / defective lifting gears immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Fall of load due to unsafe slinging | S | Property | 3 | 5 | 15 | B | 1) Use proper slinging & padding depending on the load 2) Use designated lifting lugs if available | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Fall of load due to improper signalling | S | Property | 3 | 5 | 15 | B | 1) Assign 3rd party certified rigger to give signal 2) Use radio or additional rigger in case of blind spot | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Barricade perimeter of crane lifting radius 3) No personnel allowed under the load or crane boom 4) Avoid lifting the material over head 5) Use whistle / megaphone siren to warn other personnel in the area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Hitting other structure by load during lifting | S | Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Fall of personnel from manlift basket when installing the assemble structural roof truss | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Provide a separate lifeline or use web sling wrap on installed steel component where they can tie-off their lanyards separately 3) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Fall of roof truss due to insufficient bolting and untightened nuts of bolts | S | Physical / Property | 3 | 5 | 15 | B | 1) Minimum of 60% of number of bolts must be connected for each joint 2) All bolts must be manually tightened fully using ratchet | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of structural roof truss assembly | Fall of hand tools / nuts / bolts during bolting of steel structure | S | Physical / Property | 3 | 5 | 15 | B | 1) All bolts and nuts must be placed on bucket or container 2) Hand tools provided with restraining rope and tied to prevent fall 3) No personnel allowed under the man lift boom and basket | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Overturning of crane / manlift due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Use steel plate over backfilled / uneven area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Overturning of crane due to improper set-up | S | Physical / Property | 3 | 5 | 15 | B | 1) Set-up crane outrigger minimum of 2 meters from excavation 2) Crane balance and wheels of mobile crane not touching the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Overturning of crane due to failed outrigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Outrigger must be fully extended without hydraulic leak 2) Outirigger locking pin installed 3) Outrigger pads in good condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Overturning of crane due to defective equipment during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check crane control / safety device if properly working 2) Check stability and crane condition before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Fall of load due to defective lifting gears | S | Physical / Property | 3 | 5 | 15 | B | 1) Check lifting gears before / after use 2) Remove damage / defective lifting gears immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Fall of load due to unsafe slinging | S | Property | 3 | 5 | 15 | B | 1) Use proper slinging & padding depending on the load 2) Use designated lifting lugs if available | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Fall of load due to improper signalling | S | Property | 3 | 5 | 15 | B | 1) Assign 3rd party certified rigger to give signal 2) Use radio or additional rigger in case of blind spot | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Barricade perimeter of crane lifting radius 3) No personnel allowed under the load or crane / man lift boom 4) Avoid lifting the material over head 5) Use whistle / megaphone siren to warn other personnel in the area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Hitting other structure by load during lifting | S | Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Fall of personnel from manlift basket when installing the steel purlins | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Provide a separate lifeline or web sling where they can tie-off their lanyards separately 3) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Fall of steel purlins due to insufficient bolting and untightened nuts of bolts | S | Physical / Property | 3 | 5 | 15 | B | 1) Minimum of 60% of number of bolts must be connected for each joint 2) All bolts must be manually tightened fully using ratchet | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Fall of hand tools / nuts / bolts during bolting of steel structure | S | Physical / Property | 3 | 5 | 15 | B | 1) All bolts and nuts must be placed on bucket or container 2) Hand tools provided with restraining rope and tied to prevent fall 3) Isolate the area under where the purlins will be installed. | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof purlins | Personnel hitting installed steel structure while manoeuvering the manlift | S | Physical | 3 | 4 | 12 | B | 1) Exercise caution when operating the man lift 2) Wear safety helmet with chin strap 3) Install overhead protection bar around the basket of manlift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of cladding materials to site | Collision between transport vehicle with other site vehicle due to absence of flagman | S | Physical / Property | 3 | 5 | 15 | B | 1) Conduct safety check before use of construction vehicles 2) Install safety device for construction vehicle and place the signal man | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of cladding materials to site | Collision between transport vehicle with existing site structure due to overspeeding / non observance of traffic rules | S | Property | 3 | 4 | 12 | B | 1) Vehicle follow 20 kph speed limit 2) Vehicle pass at designated road | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of cladding materials to site | Site personnel struck by transport vehicle | S | Physical | 2 | 5 | 10 | B | 1) Provide pedestrian acecss for site personnel 2) Wear personal protective equipment | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of cladding materials to site | Overturning of transport vehicle caused by bad ground condition | S | Property | 3 | 3 | 9 | C | 1) Flat and smooth ground 2) Potholes, uneven surface immediately covered | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of cladding materials to site | Material fall due to absence of trailer bed railing | S | Property | 2 | 3 | 6 | C | 1) Check safety rails of trailer bed. 2) Use steel railings and not wood / timber railings | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of cladding materials to site | Vehicle struck by protruding material from trailer bed | S | Physical / Property | 3 | 5 | 15 | B | 1) Install safety buntings or safet signage on the protruding end of the material 2) Assign escort vehicle at the rear of the trailer to alert other vehicles | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of cladding materials to site | Material fall caused by improper / unsafe stacking | S | Property | 2 | 3 | 6 | C | 1) Keep materials separately, Don't pile more than 1.5m 2) Install safety device (wood wedge) for rolling materials | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of cladding materials to site | Material fall due to unsecured load and no proper lashing | S | Property | 2 | 5 | 10 | B | 1) Cladding materials placed flat with timber spacer and tied 2) Materials secured with lashing belt | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Overturning of fork lift due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Remove unwanted materials that obstruct the pathway or working area of fork lift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Overturning of fork lift due to unbalanced lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Exercise caution when shifting cladding materials more than 6 meters in length 2) Conduct test lift to ensure center of gravity of load is between the forks of equipment | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Overturning of fork lift due to heavy load being lifted | S | Physical / Property | 3 | 5 | 15 | B | 1) Check weight of bundle of cladding materials from material delivery receipt 2) Check capacity of fork lift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Overturning of fork lift due to defective equipment during material shifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check forklift control / safety device if properly working 2) Check stability and fork lift condition before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Fall of load due to short forks | S | Property | 3 | 5 | 15 | B | 1) check dimension of materials to be lifted 2) Check if forks of equipment extend at least 12 inches from the material being lifted | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Fall of load from trailer after being pushed by forks of forklift | S | Property | 3 | 5 | 15 | B | 1) Assign banks man and no person must be allowed on the other side of the trailer bed 2) Assign qualified helper to assist forklift operator when inserting the forks of the fork lift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Fall of load due to multiple lifting | S | Property | 3 | 5 | 15 | B | 1) Do not lift multiple materials that is not secured together 2) Do not lift cladding materials of different length | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Personnel / flagman struck by forks or equipment or load being lifted / shifted | S | Physical | 3 | 5 | 15 | B | 1) Maintain minimum of 5 meter distance from the equipment 2) Use flag and whistle to give signal to the forklift operator 3) Stop equipment if other workers are nearby | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Fork lift hitting other steel structure materials stored at temporary laydown area | S | Property | 3 | 4 | 12 | B | 1) Forklift to operate at 5~10kph when shifting cladding materials 2) Use flag and whistle to give signal to the fork lift operator | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Fall of load when shifting and lifting too high | S | Property | 3 | 4 | 12 | B | 1) Lower the load as close to the ground before manoeuvring 2) Do not lift load beyond the fork lift capacity | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Unloading of cladding materials using forklift at temporary site storage area | Fall of load while shifting materials on a reverse direction | S | Property | 3 | 5 | 15 | B | 1) Avoid shifting materials on a reverse manner 2) Either place the load to the ground and shift fork lift direction so that it will be transported in a forward direction | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of cladding materials | Using uninspected power tools | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect and check power tools before using 2) Check if machine guarding and auxiliary handle available | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of cladding materials | Using power tools with frayed / damage extension cable | S | Physical / Property | 3 | 5 | 15 | B | 1) Check power tools extension cable for posssible damage / defect 2) Inspect cable connection to the power tool and male socket | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of cladding materials | Electric shock caused by inadequate insulation and absence of ELCB | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect if cable is 3-phase or double insulated 2) Check power source if provided with 30mA ELCB 3) Inspect if electrical DB is properly grounded | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of cladding materials | Hand injury due to improper use of angle grinder | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if personnel is competent to use the angle grinder 2) Check proper handling and use of power tools by worker | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of cladding materials | Dust generated during cutting of cladding materials | S | Property | 3 | 5 | 15 | B | 1) Avoid cutting of concrete blocks inside the building room 2) Utilize exhaust fan if unavoidable to dissipate dust generated | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of cladding materials | Shattering of cutting disk due to low RPM / using defective disk | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect if cutting disk RPM is higher than the power tools rated RPM 2) Inspect if disk has defect, crack or dull sound and remove immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of cladding materials | Eye / face injury from flying splinters / rockwool particles | S | Property | 3 | 5 | 15 | B | 1) Wear and use full face shield aside from safety glasses 2) Isolate area with tarpaulin to prevent rockwool particles from spreading | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Cutting of cladding materials | Fall on the same level due to poor management of cables / poor housekeeping | S | Physical | 3 | 5 | 15 | B | 1) Conduct regular housekeeping and remove waste / unwanted materials 2) Arrange electrical cable by hanging overhead using insulated S-bar or cable posts | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Overturning of crane / manlift due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Use steel plate over backfilled / uneven area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Overturning of crane due to improper set-up | S | Physical / Property | 3 | 5 | 15 | B | 1) Set-up crane outrigger minimum of 2 meters from excavation 2) Crane balance and wheels not touching the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Overturning of crane due to failed outrigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Outrigger must be fully extended without hydraulic leak 2) Outirigger locking pin installed 3. Outrigger pads in good condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Overturning of crane due to defective equipment during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check crane control / safety device if properly working 2) Check stability and crane condition before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Fall of load due to defective lifting gears | S | Physical / Property | 3 | 5 | 15 | B | 1) Check lifting gears before / after use 2) Remove damage / defective lifting gears immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Fall of load due to unsafe slinging | S | Property | 3 | 5 | 15 | B | 1) Use approved lifting gears / tackles and secure them to cladding materials properly | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Fall of load due to improper signalling | S | Property | 3 | 5 | 15 | B | 1) Assign 3rd party certified rigger to give signal 2) Use radio or additional rigger in case of blind spot | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Barricade perimeter of crane lifting radius 3) No personnel allowed under the load or crane boom 4) Use whistle / megaphone siren to warn other personnel in the area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Hitting other structure by load during lifting | S | Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on lifting activity | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Fall of wall cladding due to insufficient screw connection | S | Physical / Property | 3 | 5 | 15 | B | 1) Install more than 60 percent of the allocated screw as specified by the manufacturer | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of wall cladding materials | Fall of personnel from manlift basket when installing the wall cladding material | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Comply with 100% tie-off 3) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Overturning of crane / manlift due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Use steel plate over backfilled / uneven area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Overturning of crane due to improper set-up | S | Physical / Property | 3 | 5 | 15 | B | 1) Set-up crane outrigger minimum of 2 meters from excavation 2) Crane balance and wheels not touching the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Overturning of crane due to failed outrigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Outrigger must be fully extended without hydraulic leak 2) Outirigger locking pin installed 3) Outrigger pads in good condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Overturning of crane due to defective equipment during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check crane control / safety device if properly working 2) Check stability and crane condition before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Fall of load due to defective lifting gears | S | Physical / Property | 3 | 5 | 15 | B | 1) Check lifting gears before / after use 2) Remove damage / defective lifting gears immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Fall of load due to unsafe slinging | S | Physical / Property | 3 | 5 | 15 | B | 1) Use double choke slinging of cladding sheet when lifting and padding along the sharp edge | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Fall of load due to improper signalling | S | Physical / Property | 3 | 5 | 15 | B | 1) Assign 3rd party certified rigger to give signal 2) Use radio or additional rigger in case of blind spot | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Barricade perimeter of crane lifting radius 3) No personnel allowed under the load or crane boom 4) Use whistle / megaphone siren to warn other personnel in the area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Hitting other structure by load during lifting | S | Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Fall of personnel from the roof due to absence of fall prevention facility | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Provide a separate lifeline or web sling wrap on installed steel component where they can tie-off their lanyards separately 3) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Fall of personnel due to unsafe lifeline used | S | Physical / Property | 3 | 5 | 15 | B | 1) Regularly inspect & check installed lifeline for damage / wear / defect and ensure it is strong & stable 2) Provide individual retractable lanyard for every worker on the roof | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Fall of hand tools / screws while installing the roof cladding materials | S | Physical / Property | 3 | 5 | 15 | B | 1) All screws must be placed on bucket or container 2) Hand tools provided with restraining rope and tied to prevent fall | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of roof cladding | Fall of materials to the ground due to absence of safety net | S | Physical / Property | 3 | 5 | 15 | B | 1) Install safety net under the roof cladding area 2) Remove accumulated materials on the safety net immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of flashing sheet | Overturning of crane / manlift due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Use steel plate over backfilled / uneven area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of flashing sheet | Fall of load due to defective lifting gears | S | Physical / Property | 3 | 5 | 15 | B | 1) Check lifting gears before / after use 2) Remove damage / defective lifting gears immediately | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of flashing sheet | Fall of load due to unsafe slinging | S | Property | 3 | 5 | 15 | B | 1) Ensure rigger is 3rd party certified 2) Check if proper slinging is utilized and conduct test lift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of flashing sheet | Fall of load due to improper signalling | S | Property | 3 | 5 | 15 | B | 1) Assign 3rd party certified rigger to give signal 2) Use radio or additional rigger in case of blind spot | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of flashing sheet | Personnel struck by equipment / flashing sheet during lifting | S | Physical | 3 | 5 | 15 | B | 1) Barricade perimeter of manlift working area 2) No personnel allowed under thebasket or boom of manlift | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of flashing sheet | Fall of personnel from man basket when installing the flashing sheet | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of flashing sheet | Fall of flashing sheet due to insufficient screw connection | S | Physical / Property | 3 | 5 | 15 | B | 1) Install the specified number of screw for every given length as per manufacturer recommendation | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Installation of flashing sheet | Fall of hand tools / screws during installation of flashing sheet | S | Physical / Property | 3 | 5 | 15 | B | 1) All screws must be placed on bucket or container 2) Hand tools provided with restraining rope and tied to prevent fall 3) No personnel allowed under the manlift boom and basket | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material Shifting at site | Collision arise from falling of materials | S | Physical / Property | 2 | 4 | 8 | C | 1) Don't pile materials along the leading edge of platform 2) Install safety net and cover on all floor openings to avoid materials and personnel fall | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material Shifting at site | Fall on the same level while pushing the wheel borrow | S | Physical | 2 | 4 | 8 | C | 1) Installation degree for ramp should be less than 15 degrees 2) Install substantial footboard / wood cleats at 14 inches spacing 3) Install the necessary handrail and other safety device | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material Shifting at site | Material fall due to unsafe condition of pully | S | Property | 2 | 4 | 8 | C | 1) Check pulley safety condition before use 2) Secure pulley with wire rope instead of PP rope | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material Shifting at site | Material fall from elevated area while moving from pulley to platform | S | Property | 2 | 4 | 8 | C | 1) Check pulley condition and fix it with wire rope tightly 2) Use appropved provisioned handling device | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material Shifting at site | Overturning / tumbling due to lifting excessive weight / load | S | Physical / Property | 1 | 4 | 4 | D | 1) Lift materials less than 25 kilos 2) Utilize buddy system when lifting materials | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material Shifting at site | Overturning / tumbling caused by sliding on ramp or slope access | S | Physical | 1 | 4 | 4 | D | 1) Installation degree for ramp should be less than 15 degrees 2) Install substantial footboard / wood cleats at 14 inches spacing 3) Install the necessary handrail and other safety device | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material Shifting at site | Overturning due to absence of proper / safe access way | S | Physical / Property | 2 | 3 | 6 | C | 1) Transport and carry manageable wight of material 2) Keep safe and clear access way / path way | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material Shifting at site | Back / hand pain due to repititive movement | S | Physical | 3 | 3 | 9 | C | 1) Lift materials less than 25 kilos 2) Provide breaks to break monotony of movement | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Material Shifting at site | Slip, trip and fall due to poor housekeeping in the work area | S | Property | 2 | 3 | 6 | C | 1) Remove unwanted / waste materials immediately 2) Arrange electrical cables and hang them overhead | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Using uninspected power tools | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect and check power tools before using 2) Check if machine guarding and auxiliary handle available | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Using power tools with frayed / damage extension cable | S | Physical / Property | 3 | 5 | 15 | B | 1) Check power tools extension cable for posssible damage / defect 2) Inspect cable connection to the power tool and male socket | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Electric shock caused by inadequate insulation and absence of ELCB | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect if cable is 3-phase or double insulated 2) Check power source if provided with 30mA ELCB 3) Inspect if electrical DB is properly grounded | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Hand injury due to improper use of chipping gun | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if personnel is competent to use the chipping gung 2) Check proper handling and use of power tools by worker | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Dust accumulated during chipping activity | S | Physical | 3 | 5 | 15 | B | 1) Provide ventilation fan to help dissipate dust geenrated 2) Worker to wear / use dust mask or cartridge filter mask | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Damaging the ear due to excessive noise while using the chipping gun | S | Physical | 3 | 5 | 15 | B | 1) Wear and use ear protective equipment, ear plugs or ear muffs | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Eye / face injury from flying splinters / particles | S | Physical | 3 | 5 | 15 | B | 1) Wear and use full face shield aside from safety glasses | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Fall on the same level due to poor management of cables / poor housekeeping | S | Physical | 3 | 5 | 15 | B | 1) Conduct regular housekeeping and remove waste / unwanted materials 2) Arrange electrical cable by hanging overhead using insulated S-bar or cable posts | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Back / hand / body pain due to repititive movement | S | Physical | 3 | 3 | 9 | C | 1) Assign buddy system to prevent prolong use of power tool 2) Provide frequent breaks to break monotony of movement | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Overturning due to bad condition of scaffold structure | S | Physical | 3 | 5 | 15 | B | 1) Scaffold Inspector to inspect the scaffold structure before use 2) Wear and use full body harness | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Personnel fall due to absence of appropriate access ladder | S | Physical | 3 | 2 | 6 | C | 1) Install the necessary access ladder leading to the working platform of the mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Personnel fall caused by not wearing safety harness | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Comply with 100% tie-off 3) Before height work, practice double hook demonstration 4) Workers must attend Work at Heights safety training | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Personnel fall due to absence of safety rail and safety belt | S | Physical | 3 | 2 | 6 | C | 1) Install standard height guard rail / safety rail on all sides 2) Wear and use full body harness when working on mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Fall because of absence of cover at openings | S | Physical | 3 | 4 | 12 | B | 1) Install cover on all floor opening and safety guard to prevent falling 2) Provide appropriate safety / warning signage | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Chipping Works | Personnel fall because of using damaged ladder | S | Physical | 3 | 4 | 12 | B | 1) Avoid using straight ladder as working platform and made of wood 2) use step / A-type ladder of approved materials 3) Check step ladder condition before use and assign worker to hold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Using uninspected equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect and check equipment (one bagger mixer) before using 2) Check if machine guarding for rotating parts installed | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Caught in / entanglement because of carelessness when placing materials on drum of mixer | S | Physical | 2 | 3 | 6 | C | 1) Exercise caution and avoid wearing loose clothing / safety gloves when placing plastering materials on the drum of mixer 2) Isolate mixing area and maintain safe distance when equipment is mixing the plaster mix | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Tumbling / slip of worker due to improper use of equipment | S | Physical | 1 | 3 | 3 | D | 1) Assign trained worker to operate equipment 2) Check emergency stop button of equipment before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Eye splash of chemical during mixing | S | Physical | 1 | 4 | 4 | D | 1) Follow instructions based on MSDS 2) Wear Personal protective equipment / full face shield 3) Provide emergency eye wash at the work area | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Fall on the same floor due to scattered materials | S | Physical | 3 | 3 | 9 | C | 1) Conduct housekeeping and remove loose materials from the ground | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Soil pollution due to spill of concrete mix on the ground | S | Environmental | 2 | 4 | 8 | C | 1) Provide secondary containment / drip tray to contain slurry concrete from contaminating the ground soil 2) Conduct regular housekeeping and removed hardened plaster mix | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Breathing difficulty after inhaling cement dust when placing / mixing the plaster in the equipment | S | Physical / Health | 3 | 4 | 12 | B | 1) Provide and use dust mask / cartridge mask 2) Isolate mixing area and maintain safe distance during placing of materials and mixing | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Fall due to unsafe installation of fall prevention facility | S | Physical / Property | 3 | 5 | 15 | B | 1) Install safe, secure and appropriate height safety rail 2) Secure material properly from the platform 3) Wear and tie-off the full body harness | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Material fall while moving during plastering work | S | Physical | 3 | 5 | 15 | B | 1) Distance of platform from edge within 20cm 2) Install complete planking of platform without gap | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Material fall due excessive storing of materials on the platform | S | Property | 3 | 4 | 12 | B | 1) Install safety rail and toe board along the platform edge 2) Install safety net for additional fall prevention 3) Avoid storing excessive amount / quantity of materials on the platform | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Overturning due to bad condition of scaffold structure | S | Physical | 3 | 5 | 15 | B | 1) Scaffold Inspector to inspect the scaffold structure before use 2) Wear and use full body harness | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall from moving along the elevated area | S | Physical | 3 | 5 | 15 | B | 1) Install safety rail on the edge 2) Wear full body hanress and install lifeline to tie-off | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall while leaning over the safety rail | S | Physical | 3 | 3 | 9 | C | 1) Install the safety rail properly 2) Wear full body harness and follow 100% tie-off policy | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Hazard of overturning due to narrow platform | S | Physical / Property | 3 | 3 | 9 | C | 1) Working platform width minimum of 60cm 2) Maintain secured and full planking working platform | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personel fall when lifeline being used is unhinged | S | Physical | 2 | 5 | 10 | B | 1) Check and daily inspect lifeline condition and restraining condition 2) Check anchorage poits of lifeline | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall while working on the cantilever scaffold with wide gap from the wall | S | Physical | 2 | 5 | 10 | B | 1) Tie-off lanyards of full body harness to an auxiliary lifeline 2) Secure lifeline properly and regularly check its condition | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall while stepping on damaged platform | S | Physical | 2 | 4 | 8 | C | 1) Check safety condition of platform before use 2) Personnel to wear full body harness and follow 100% tie-off policy | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Eye damage because of absence of personal protective equipments | S | Physical | 2 | 4 | 8 | C | 1) Wear safety goggles or full face shield | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Respiratory disease caused by scattered dust / inadequate ventilation | S | Physical / Health | 2 | 4 | 8 | C | 1) Provide enough ventilation / exhaust in the workplace 2) Wear and use dust mask or cartidge filter mask | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Material fall caused by rope snapping while lifting the bucket of mortar | S | Physical / Property | 2 | 4 | 8 | C | 1) Check the PP rope before use | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Tumbling and collision between worker due to insufficient lighting | S | Physical | 2 | 3 | 6 | C | 1) Provide enough lighting with more than 60 Lux illumination at the work site | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Accident caused while hammering nail on the wall | S | Physical | 1 | 4 | 4 | D | 1) Wear safety glasses / goggles | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Overturning / personnel fall due to sudden movement of mobile scaffold for failure to lock caster wheels | S | Physical / Property | 3 | 3 | 9 | C | 1) Check safety condition of mobile scaffold before use 2) Inspect and check if caster wheels of mobile scaffold are locked | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Material fall because because of absence of toe board on scaffold platform | S | Physical / Property | 2 | 2 | 4 | D | 1) Install toe board on all platform edges 2) Install additional safety net if practicable | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Overturning due to absence of adequate support / bracing for mobile scaffold | S | Physical / Property | 3 | 2 | 6 | C | 1) Install the necessary diagonal bracing support for the mobile scaffold 2) Install plan bracing to prevent twisting of mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Overturning due of absence of outrigger on mobile scaffold | S | Physical / Property | 3 | 1 | 3 | D | 1) Install appropriate ourigger supprot to prevent overturning 2) Install safety alarm device for overturning | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall from ladder scaffold and mobile ladder | S | Physical | 3 | 3 | 9 | C | 1) Check the condition of the access ladder 2) Install the appropriate access ladder for the mobile scaffold 3) Working platform fully planked and opening covered | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Fall caused by unsafe condition of locking and strength of mobile scaffold | S | Physical | 3 | 2 | 6 | C | 1) Fix platform tightly on mobile scaffold 2) Wear and use full body harness 3) Check lock of caster wheels are engaged | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall from mobile scaffold when moved while working | S | Physical | 3 | 2 | 6 | C | 1) Do not move mobile scaffold while personnel are working or on top of the mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall due to absence of appropriate access ladder | S | Physical | 3 | 2 | 6 | C | 1) Install the necessary access ladder leading to the working platform of the mobile scaffold | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Overturning / personnel fall due to sudden movement of mobile scaffold for failure to lock caster wheels | S | Physical / Property | 3 | 3 | 9 | C | 1) Check safety condition of mobile scaffold before use 2) Inspect and check if caster wheels of mobile scaffold are locked | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Fall from ladder while carrying tools / materials | S | Physical / Property | 3 | 4 | 12 | B | 1) Maintain 3-point contact when climbing a ladder 2) Do not carry tools / materials by hand when climbing the ladder 3) Use belt bags to strap hand tools | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Fall on the same level due to poor management of cables / poor housekeeping | S | Physical | 3 | 5 | 15 | B | 1) Conduct regular housekeeping and remove waste / unwanted materials 2) Arrange electrical cable by hanging overhead using insulated S-bar or cable posts | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Interior work | Fall due to being caught off balance along the balcony | S | Physical | 3 | 5 | 15 | B | 1) Install temporary safety rail and wear / use full body harness | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Interior work | Overturning / tumbling due to unsecured / obstructing material | S | Physical | 3 | 3 | 9 | C | 1) Conduct regular housekeeping and remove unwanted materials | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E
false | Interior work | Overturning / tumbling because of using improvised / unsafe temporary working platform instead of proper work bench | S | Physical | 3 | 3 | 9 | C | 1) Footboard width should be more than 40cm, less than 2m length, less than 80cm height | Dongil Lee | 2024-01-31 | 1 | 1 | 1 | E