## Sheet1
삭제 Del | 작업활동 및 내용 Work & Contents | 유해위험요인 및 환경측면 영향 Hazard & Risk | EHS | 피해형태 및 환경영향 Damage & Effect | 위험성 Risk Rate | 위험성 Risk Rate.1 | 위험성 Risk Rate.2 | 등급 Rate | 개선대책 및 세부관리방안 Corrective Action | 개선담당자 Responsibility | 개선일자 Action Date | 위험성 Risk Rate | 위험성 Risk Rate.1 | 위험성 Risk Rate.2 | 등급 Rate
삭제 Del | 작업활동 및 내용 Work & Contents | 유해위험요인 및 환경측면 영향 Hazard & Risk | EHS | 피해형태 및 환경영향 Damage & Effect | 빈도 Risk Rate | 강도 Severity | T | 등급 Rate | 개선대책 및 세부관리방안 Corrective Action | 개선담당자 Responsibility | 개선일자 Action Date | 빈도 Likelihood | 강도 Severity | T | 등급 Rate
false | In and Out of materials | Material fall caused by improper / unsafe handling of material while using crane | S | Physical / Property | 3 | 4 | 12 | B | 1) Check safe lifting requirement for materials more than 10tons weight 2) Check safety condition of equipment / lifting gears before use 3) Lifting work should be conducted by 3rd party certified personnel 4) Exercise 3-3-3 safe lifting practices | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material fall due to unsecured load and no proper lashing | S | Physical / Property | 2 | 5 | 10 | B | 1) Materials placed on rack or box and tied 2) Materials secured with lashing belt | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material fall caused by improper / unsafe stacking | S | Physical / Property | 2 | 3 | 6 | C | 1) Keep materials separately, Don't pile more than 1.5m 2) Install safety device (wood wedge) for rolling materials 3) Keep materials inside packing box / racks | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material / Equipment fall due to unsecured loading and exceeding load capacity | S | Property | 2 | 5 | 10 | B | 1) Conduct inspection of materials more than 10 Tons in weight 2) Lifting to be conducted by 3rd party certified crane operator / rigger 3) Use appropriate equipment to unload materials 4) Crane outrigger fully extended and equipment set on stable / smooth ground 5) Materials properly lashed & secure before lifting | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collision between transport vehicle with existing site structure due to overspeeding / non observance of traffic rules | S | Property | 3 | 4 | 12 | B | 1) Vehicle follow 20 kph speed limit 2) Vehicle pass at designated road | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collision of equipment / vehicle due to inconsistent traffic signages | S | Physical / Property | 2 | 2 | 4 | D | 1) Standardizeall traffic / safety signage at the work site 2) Assign trained flagman for every equipment | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Overturning of transport vehicle caused by bad ground condition | S | Property | 3 | 3 | 9 | C | 1) Flat and smooth ground 2) Potholes, uneven surface immediately covered | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Overturning because workers failed to conduct housekeeping at the workplace | S | Physical / Property | 1 | 2 | 2 | E | 1) Conduct safety inspection for materials more than 10 Tons in weight 2) Check equipment safety condition using chesklit before use 3) Lifting work should be conducted by trained worker 4) Use 3rd party certified material box 5) Check the safety condition of all ligting gears / tackles 6) Conduct regualr housekeeping at the workplace | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Site personnel struck by transport vehicle | S | Physical | 2 | 5 | 10 | B | 1) Provide pedestrian acecss for site personnel 2) Wear personal protective equipment | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse / erosion of excavation wall due to unsafe sloping and absence of sloping protection | S | Physical / Property | 3 | 4 | 12 | B | 1) Comply with the side sloping based on the soil classification 2) Install safety net as additional protection against erosion | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of excavation wall / slope caused by unstable ground and change of ground-water level | S | Physical / Property | 2 | 4 | 8 | C | 1) Follow proper sloping depending on soil classification 2) Provide dewatering equipment to remove accumulated water and prevent scouring of excavation base 3) Install safety net for the excavation side slope | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of excavation wall due to failure to regularly check the geological features | S | Physical / Property | 3 | 4 | 12 | B | 1) Immediately Work stop 2) Check and modify the method of construction based on the current soil / ground condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of excavation wall caused by excessive stacking of materials | S | Physical / Property | 2 | 2 | 4 | D | 1) Avoid stockpiling materials along the retaining wall 2) Remove immediately excavation spoils from the area | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of excavation wall due to uncontrolled groundwater | S | collapse | 2 | 3 | 6 | C | 1) Comply with standards for sloping requirement for excavation based on soil classificiation 2) Follow safe work methodology of construction and provide enoughdewatering equipment 3) Regularly check excavation / dewatering condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of backfill materials due to subsidence of mud and sand in the area | S | Physical / Property | 2 | 3 | 6 | C | 1) Follow safe work methodology for backfilling activity 2) Regularly check the site condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of excavation wall due to change in earth pressure caused by discharge of underground water | S | Physical / Property | 2 | 3 | 6 | C | 1) Comply with standards for sloping requirement for excavation based on soil classificiation 2) Follow safe work methodology of construction and provide enough dewatering equipment 3) Regularly check excavation / dewatering condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of excavation wall caused by increased / excessive earth pressure | S | Physical / Property | 2 | 3 | 6 | C | 1) Comply with standards for sloping requirement for excavation based on soil classificiation 2) Follow safe work methodology of construction and provide enough dewatering equipment 3) Regularly check excavation / dewatering condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collision between equipment while traveling along the slope of excavation | S | Physical / Property | 2 | 4 | 8 | C | 1) Assign enough flagman to direct traffic along the access slope 2) Ensure slope access is wide enough for equipment and maintain gradual sloping (less than 20 degrees) | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Overturning due to unstable / backfilled ground for equipment | S | Physical / Property | 2 | 3 | 6 | C | 1) Ensure stable, compact and level ground 2) Use metal plate if equipment is set up on backfilled ground | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Overturning caused by carelessness in signaling during reversing of dump truck | S | Physical / Property | 2 | 5 | 10 | B | 1) Check equipment condition using checklist before use 2) Install safety device for equipment and assign flagman 3) Install wood stopper to prevent dump truck from skidding | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Vehicle / equipment fall because of absence of safety rail | S | Physical / Property | 2 | 4 | 8 | C | 1) Install hard barricade / guard rail along the excavation perimeter 2) Wear personal protective equipments | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Personnel fall because of absence of safety rail around the excavation | S | Physical | 3 | 5 | 15 | B | 1) Install hard barricade / guard rail along the excavation perimeter 2) Wear personal protective equipments | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Personnel strike by equipment while using the access slope | S | Physical | 2 | 4 | 8 | C | 1) Assign separate access for personnel along the access slope 2) Install hard barricade as demarkation between equipment and personnel access with safety signage | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Personnel fall / tumble due to absence of safe pathway | S | Physical | 2 | 4 | 8 | C | 1) Provide proper temporary access with hand rails 2) Remove obstruction from the access way | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Personnel falling because of absence of safety rail around the excavation | S | Physical | 3 | 5 | 15 | B | 1) Install hard barricade / guard rail along the excavation perimeter 2) Wear personal protective equipments | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Personnel fall while inspecting along the excavation edge | S | Physical | 2 | 3 | 6 | C | 1) Wear personal protective equipments 2) Install safety rail along the edge of excavation | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Collapse caused by inadequate investigation of geological features | S | Physical / Property | 2 | 4 | 8 | C | 1) Follow and comply proper side sloping based on soil classification 2) Install the earth dike / berm and safety net against soil erosion 3) Check safety condition for slope with earth anchor and shotcrete 4) Investigate the soil condition in the work site | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Personnel fall / tumble due to absence of safe pathway | S | Physical | 2 | 4 | 8 | C | 1) Provide proper temporary access with hand rails 2) Remove obstruction from the access way | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Collision due to inexperienced and unlicensed driver | S | Physical / Property | 3 | 5 | 15 | B | 1) Check driver's license before allowing personnel to drive vehicle 2) Check vehicle safety before driving using BLOWBAG | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Collision during unsafe reversing of construction equipment / vehicle | S | Physical / Property | 3 | 5 | 15 | B | 1) Check equipment / vehicle safety using checklist / BLOWBAG before use 2) Install reverse / collision alarm of equipment and assign flagman 3) Install earth dike / mound along excavation edge | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Overturning / fall of equipment due to misuse | S | Physical / Property | 3 | 4 | 12 | B | 1) Check equipment safety using checklist / BLOWBAG before use 2) Use equipment as per manufacturers recommendation | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Overturning / tumbling of worker during reversing of excavator | S | Physical / Property | 3 | 5 | 15 | B | 1) Install reverse alarm and assign trained flagman 2) Ensure slope is gradual and remove obstructions from access | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Personnel fall caused by carelessness of workers and insufficient lighting | S | Physical | 2 | 5 | 10 | B | 1) Provide enough lighting with more than 60 Lux illumination at the work site | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Fall caused by inadequate checking of equipment | S | Physical / Property | 2 | 3 | 6 | C | 1) Ensure equipment is inspected by Doosan and operation permit is attached 2) Conduct daily inspection of equipment using appropriate checklist | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material fall caused by improper / unsafe handling of material while using crane | S | Physical / Property | 3 | 4 | 12 | B | 1) Check safe lifting requirement for materials more than 10tons weight 2) Check safety condition of equipment / lifting gears before use 3) Lifting work should be conducted by 3rd party certified personnel | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material fall due to unsecured load and no proper lashing | S | Physical / Property | 2 | 5 | 10 | B | 1) Materials placed on rack or box and tied 2) Materials secured with lashing belt | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material fall caused by improper / unsafe stacking | S | Physical / Property | 2 | 3 | 6 | C | 1) Keep materials separately, Don't pile more than 1.5m 2) Install safety device (wood wedge) for rolling materials 3) Keep materials inside packing box / racks | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material / Equipment fall due to unsecured loading and exceeding load capacity | S | Property | 2 | 5 | 10 | B | 1) Conduct inspection of materials more than 10 Tons in weight 2) Lifting to be conducted by 3rd party certified crane operator / rigger 3) Use appropriate equipment to unload materials 4) Crane outrigger fully extended and equipment set on stable / smooth ground 5) Materials properly lashed & secure before lifting | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collision between transport vehicle with existing site structure due to overspeeding / non observance of traffic rules | S | Property | 3 | 4 | 12 | B | 1) Vehicle follow 20 kph speed limit 2) Vehicle pass at designated road | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collision of equipment / vehicle due to inconsistent traffic signages | S | Physical / Property | 2 | 2 | 4 | D | 1) Standardizeall traffic / safety signage at the work site 2) Assign trained flagman for every equipment | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Overturning of transport vehicle caused by bad ground condition | S | Property | 3 | 3 | 9 | C | 1) Flat and smooth ground 2) Potholes, uneven surface immediately covered | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Overturning because workers failed to conduct housekeeping at the workplace | S | Physical / Property | 1 | 2 | 2 | E | 1) Conduct safety inspection for materials more than 10 Tons in weight 2) Check equipment safety condition using chesklit before use 3) Lifting work should be conducted by trained worker 4) Use 3rd party certified material box 5) Check the safety condition of all ligting gears / tackles 6) Conduct regualr housekeeping at the workplace | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Site personnel struck by transport vehicle | S | Physical | 2 | 5 | 10 | B | 1) Provide pedestrian acecss for site personnel 2) Wear personal protective equipment | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse / erosion of excavation wall due to unsafe sloping and absence of slope protection | S | Physical / Property | 3 | 4 | 12 | B | 1) Comply with the side sloping based on the soil classification 2) Install safety net as additional protection against erosion | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collision between equipment while traveling along the slope of excavation | S | Physical / Property | 2 | 4 | 8 | C | 1) Assign enough flagman to direct traffic along the access slope 2) Ensure slope access is wide enough for equipment and maintain gradual sloping (less than 20 degrees) | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Vehicle / equipment fall because of absence of safety rail | S | Physical / Property | 2 | 4 | 8 | C | 1) Install hard barricade / guard rail along the excavation perimeter 2) Wear personal protective equipments | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Overturning of equipment / vehicle caused by insufficient traffic / safety signage entering / exiting the area | S | Physical / Property | 2 | 5 | 10 | B | 1) Inspect equipment / vehicle before start of activity 2) Install safety device for construction equipment / vehicle and assign flagman / banks man 3) Install the earth dike or earth mound | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Overturning caused by carelessness in signaling during reversing of dump truck | S | Physical / Property | 2 | 5 | 10 | B | 1) Check equipment condition using checklist before use 2) Install safety device for equipment and assign flagman 3) Install wood stopper to prevent dump truck from skidding | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Overturning due to noncompliance with regulations and safety device | S | Property | 2 | 3 | 6 | C | 1) Keep materials separately, Don't pile more than 1.5m 2) Install safety device (wedge) for unloading and rolling materials | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Personnel falling because of absence of safety rail around the excavation | S | Physical | 3 | 5 | 15 | B | 1) Install appropriate Fixed hard safety rail along the excavation perimeter 2) Wear personal protective equipment | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Personnel strike by equipment while using the access slope | S | Physical | 2 | 4 | 8 | C | 1) Assign separate access for personnel along the access slope 2) Install hard barricade as demarkation between equipment and personnel access with safety signage | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Personnel fall / tumble due to absence of safe pathway | S | Physical | 2 | 4 | 8 | C | 1) Provide proper temporary access with hand rails 2) Remove obstruction from the access way | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Personnel fall due to poor condition of wheel borrow during hauling of sand | S | Physical | 2 | 4 | 8 | C | 1) Check safety condition of wheel borrow 2) Avoid hauling or overloading the wheel borrow | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Personnel fall caused by carelessness of workers and insufficient lighting | S | Physical | 2 | 5 | 10 | B | 1) Provide enough lighting with more than 60 Lux illumination at the work site | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collapse of excavation wall / slope caused by unstable ground and change of ground-water level | S | Physical / Property | 2 | 4 | 8 | C | 1) Follow proper sloping depending on soil classification 2) Provide dewatering equipment to remove accumulated water and prevent scouring of excavation base 3) Install safety net for the excavation side slope | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of excavation wall during installation of pipe headers for dewatering works | S | Physical / Property | 2 | 4 | 8 | C | 1) Comply with the side sloping based on the soil classification 2) Install safety net as additional protection against erosion | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collapse of excavation wall due to failure to regularly check the geological features | S | Physical / Property | 3 | 4 | 12 | B | 1) Immediately Work stop 2) Check and modify the method of construction based on the current soil / ground condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of excavation wall due to change in earth pressure caused by discharge of underground water | S | Physical / Property | 2 | 3 | 6 | C | 1) Comply with standards for sloping requirement for excavation based on soil classificiation 2) Follow safe work methodology of construction and provide enough dewatering equipment 3) Regularly check excavation / dewatering condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collapse of excavation wall caused by excessive stacking of materials along excavation edge | S | Physical / Property | 2 | 2 | 4 | D | 1) Avoid stockpiling materials along the excavation edge 2) Remove excavation spoils immediately | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of excavation wall due to uncontrolled groundwater | S | collapse | 2 | 3 | 6 | C | 1) Comply with standards for sloping requirement for excavation based on soil classificiation 2) Follow safe work methodology of construction and provide enough dewatering equipment 3) Regularly check excavation / dewatering condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collapse of excavation wall caused by increased / excessive earth pressure | S | Physical / Property | 2 | 3 | 6 | C | 1) Comply with standards for sloping requirement for excavation based on soil classificiation 2) Follow safe work methodology of construction and provide enough dewatering equipment 3) Regularly check excavation / dewatering condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Collapse of excavation wall due to absence of slope protection and improper side slope | S | Physical / Property | 3 | 4 | 12 | B | 1) Check excavation integrity and side slope to conform with MS 2) Install safety net along excavation slope or provide retaining wall | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collapse of backfill materials due to subsidence of mud and sand in the area | S | Physical / Property | 2 | 3 | 6 | C | 1) Follow safe work methodology for backfilling activity 2) Regularly check the site condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Excavation and backfilling | Subsidence of sand due to uncontrolled underground water | S | Physical / Property | 2 | 3 | 6 | C | 1) Follow safe work methodology of construction and provide / conduct dewatering activity | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Hand and backache due to unsafe / improper handling of materials | S | Physical | 2 | 3 | 6 | C | 1) Ensure two-person team during manual handling of materials 2) Allow workers to carry less than 25 kilos of weight only | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Personnel fall because of absence of safety rail around the excavation | S | Physical | 3 | 5 | 15 | B | 1) Install appropriate hard safety rail along the excavation perimeter | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Personnel fall while inspecting along the excavation edge | S | Physical | 2 | 3 | 6 | C | 1) Wear personal protective equipments 2) Install safety rail along the edge of excavation | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Personnel fall / tumble due to absence of safe pathway | S | Physical | 2 | 4 | 8 | C | 1) Provide proper temporary access with hand rails 2) Remove obstruction from the access way | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Excavation collapse caused by inadequate investigation of geological features | S | Physical / Property | 2 | 4 | 8 | C | 1) Follow and comply proper side sloping based on soil classification 2) Install the earth dike / berm and safety net against soil erosion 3) Check safety condition for slope with earth anchor and shotcrete 4) Investigate the soil condition in the work site | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Material fall due improper & unsafe handling / tranport | S | Physical / Property | 3 | 5 | 15 | B | 1) Secure materials properly before transporting with lashing belt 2) Provide safety net cover to prevent material fall | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Material fall due to carelessness in using the lifting rope | S | Property | 3 | 4 | 12 | B | 1) Check the lifting device for damage, defect and wear 2) Immediately remove or quarantine damaged lifting device / gears | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Collision due to inexperienced and unlicensed driver | S | Physical / Property | 3 | 5 | 15 | B | 1) Check driver's license before allowing personnel to drive vehicle 2) Check vehicle safety before driving using BLOWBAG | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Collision during unsafe reversing of construction equipment / vehicle | S | Physical / Property | 3 | 5 | 15 | B | 1) Check equipment / vehicle safety using checklist / BLOWBAG before use 2) Install reverse / collision alarm of equipment and assign flagman 3) Install earth dike / mound along excavation edge | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Overturning / fall of equipment due to misuse | S | Physical / Property | 3 | 4 | 12 | B | 1) Check equipment safety using checklist / BLOWBAG before use 2) Use equipment as per manufacturers recommendation | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Overturning / tumbling of worker during reversing of excavator | S | Physical / Property | 3 | 5 | 15 | B | 1) Install reverse alarm and assign trained flagman 2) Ensure slope is gradual and remove obstructions from access | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Electric shock caused by carelessness in using welding machine, electric motor and motor pump. | S | Physical | 3 | 4 | 12 | B | 1) Use proper socket and plug with grounding and 3 Phase electrical cable 2) Connect extension cable on electrical DB with 30mA ELCB / RCB / GFCI | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Electric shock because of carelessness during repair of dewatering pump | S | Physical | 2 | 4 | 8 | C | 1) Ensure pump is powered off before conducting any repair 2) Check cable / cable connections and ensure pump body grounding | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Electrocution / electrical shock due to frayed / damaged electrical wire | S | Physical | 2 | 4 | 8 | C | 1) Check extension cables for frayed, damaged or exposed wire 2) Use proper socket and plug with grounding and 3 Phase electrical cable | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Fall caused by inadequate checking of equipment | S | Physical / Property | 2 | 3 | 6 | C | 1) Ensure equipment is inspected by Doosan and operation permit is attached 2) Conduct daily inspection of equipment using appropriate checklist | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of scaffold materials to site | Collision between transport vehicle with other site vehicle due to absence of flagman | S | Physical / Property | 3 | 5 | 15 | B | 1) Conduct safety check before use of construction vehicles 2) Install safety device for construction vehicle and assign flagman | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of scaffold materials to site | Collision between transport vehicle with existing site structure due to overspeeding / non observance of traffic rules | S | Property | 3 | 4 | 12 | B | 1) Vehicle follow 20 kph speed limit 2) Vehicle pass at designated road | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of scaffold materials to site | Site personnel struck by transport vehicle | S | Physical | 2 | 5 | 10 | B | 1) Provide pedestrian acecss for site personnel 2) Wear personal protective equipment | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of scaffold materials to site | Overturning of transport vehicle caused by bad ground condition | S | Property | 3 | 3 | 9 | C | 1) Flat and smooth ground 2) Potholes, uneven surface immediately covered | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of scaffold materials to site | Material fall due to absence of trailer bed railing | S | Property | 2 | 3 | 6 | C | 1) Check safety rails of trailer bed. 2) Use steel railings and not wood / timber railings | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of scaffold materials to site | Material fall caused by improper / unsafe stacking | S | Property | 2 | 3 | 6 | C | 1) Keep materials separately, Don't pile more than 1.5m 2) Install safety device (wood wedge) for rolling materials 3) Keep materials inside packing box / racks | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Transport / Delivery of scaffold materials to site | Material fall due to unsecured load and no proper lashing | S | Property | 2 | 5 | 10 | B | 1) Scaffold materials placed on rack and tied 2) Materials secured with lashing belt | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Manual unloading of scaffold materials | Struck by scaffold materials due to improper passing | S | Physical | 3 | 4 | 12 | B | 1) Assign enough personnel for the activity | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Manual unloading of scaffold materials | Material fall due to unsafe passing | S | Property | 3 | 4 | 12 | B | 1) Personnel to wear proper PPE, leather or rubber coated hand gloves 2) Avoid throwing materials and pass by hand only | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Manual unloading of scaffold materials | Fall on the same floor due to scattered materials | S | Physical | 3 | 3 | 9 | C | 1) Conduct housekeeping and remove loose materials on the ground | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Manual unloading of scaffold materials | Back / hand pain due to repititive movement | S | Physical | 3 | 3 | 9 | C | 1) Lift materials less than 25 kilos 2) Provide regular rest breaks to break monotony of movement | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Overturning of crane due to uneven ground | S | Physical / Property | 3 | 5 | 15 | B | 1) Ground must be level, stable and compact 2) Use steel plate over backfileld / uneven area | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Overturning of crane due to improper set-up | S | Physical / Property | 3 | 5 | 15 | B | 1) Set-up crane outrigger minimum of 2 meters from excavation 2) Crane balance and wheels not touching the ground | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Overturning of crane due to failed outrigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Outrigger must be fully extended without hydraulic leak 2) Outirigger locking pin installed 3. Outrigger pads in good condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Overturning of crane due to defective equipment during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Check crane control / safety device if properly working 2) Check stability and crane condition before use | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Fall of load due to defective lifting gears | S | Physical / Property | 3 | 5 | 15 | B | 1) Check lifting gears before / after use 2) Remove damage / defective lifting gears immediately | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Fall of load due to lifting unsecured materials | S | Property | 3 | 5 | 15 | B | 1) Lift only scaffold standard, ledger & transom if placed on racks 2) Avoid lifting materials placed on wood pallet or wood box | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Fall of load due to unsafe slinging | S | Property | 3 | 5 | 15 | B | 1) Use proper slinging & padding depending on the load 2) Use designated lifting lugs if available 3) Avoid lifting multiple materials of different configuration | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Fall of load due to bad weather condition | S | Property | 3 | 5 | 15 | B | 1) No lifting if wind speed more than 10m/s or 36kph 2) No lifting during heavy rain, sand storm or foggy condition | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Fall of load due to improper signalling | S | Property | 3 | 5 | 15 | B | 1) Only assigned 3rd party certified rigger to give signal 2) Use radio or additional rigger in case of blind spot | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Barricade the radius of the lifting area 3) No personnel allowed under the load or crane boom 4) Use whistle / megaphone siren to warn personnel | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Lifting of scaffold materials using mobile crane | Hitting other structure by load during lifting | S | Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Instalaltion / Removal of safety net | Personnel fall during installation / removal of safety net | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness and attached them on temporary lifeline or secured anchorage | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Instalaltion / Removal of safety net | Fall due to removal of safety net along the railing | S | Property | 1 | 5 | 5 | C | 1) Check and monitor safety condition during work progress 2) Install required fall protection and workers to wear / use full body harness | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Instalaltion / Removal of safety net | Fall caused due to poor material used for safety net | S | Physical / Property | 1 | 4 | 4 | D | 1) Secure all materials / equipment and avoid storing them near the edge 2) Check & monitor safety of personnel during the work progress | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Personnel fall cause by not wearing safety harness | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lifeline 2) Comply with 100% tie-off 3) Before height work, practice double hook demonstration 4) Workers must attend Work at Heights safety training | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Personnel fall due to absence of safety rail | S | Physical | 3 | 5 | 15 | B | 1) Install safety rail and wear safety belt for worker in elevated area | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Material dropped intentionally by scaffolder specially during dismantling due to lack of supervision | S | Property | 3 | 4 | 12 | B | 1) Do not multi-task and avoid dropping scaffold materials 2) Comply with the standards for scaffold erection 3) Assign drop zone and strictly control activity | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Fall of materials due to of absence of safety net and toe board | S | Physical / Property | 3 | 4 | 12 | B | 1) Remove all loose materials from platform 2) Install toe board and safety net if available | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Fall and collapse caused by dismantling of wall connection and bracket | S | Physical / Property | 3 | 5 | 15 | B | 1) Remove wall connection / ties sytematically 2) Remove them as you progress removing each lift 3) Comply with the standard and conduct the special safety training | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Fall of personnel/material due to improper/unsafe sequence for scaffold work | S | Physical / Property | 3 | 4 | 12 | B | 1) Conduct the Special safety training 2) Wear personal protective eqipments | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Fall due to unsecured/incomplete planking of working platform | S | Physical / Property | 3 | 5 | 15 | B | 1) Secure all wood planks with board clamp & maintain proper lapping 2) Install wood planks with maximum of 1 inch gap between planks | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Personal injury when using damage or improvised hand tools | S | Physical | 4 | 3 | 12 | B | 1) Check hand tools for damage or defect 2) Remove improvised, damage or defective hand tools from work site | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Fall of Hand tools (ratchet / hammer) from elevated area | S | Physical / Property | 3 | 5 | 15 | B | 1) Secure all hand tools with PP rope and tie on safety harness or hand 2) Remove hand tools left unattended | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Electric shock due to electrical cables when workers install / dismantle scaffold | S | Physical | 3 | 5 | 15 | B | 1) Remove or disconnect any cable that interfere with scaffold works 2) Provide insulation cover if cable cannot be removed 3) If possible, bury cable to avoid interference with structure | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Scaffold overturn due to absence of outrigger / raker | S | Physical / Property | 3 | 5 | 15 | B | 1) Install outrigger / raker before continuing with any work 2) If outrigger or raker is not feasible, use ties with existing structure | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Scaffold overturning due to lack of wall connection | S | Physical / Property | 3 | 5 | 15 | B | 1) Install wall connection every 5m in height / 5m in length 2) Use ties whenever possible | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Overturning of scaffold due to installed sheets | S | Physical / Property | 3 | 5 | 15 | B | 1) Remove any sheet, tarpaulin, canvass that can affect the stability of the scaffold structure | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Scaffold collapse due to usage of damage / scaffold materials | S | Physical / Property | 2 | 4 | 8 | C | 1) Inspect / check all scaffold materials and components to be used 2) Discard from service damage planks, bent / deformed pipes and other scaffold materials | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Scaffold collapse due to unsafe connection of scaffold components | S | Physical / Property | 2 | 4 | 8 | C | 1) Check the connection of scaffold materials 2) Check the quality of scaffold materials used | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Scaffold collapse due to absence of structural calculation | S | Physical / Property | 3 | 5 | 15 | B | 1) Conduct structural computation / calculation for scaffold structure more than 10 meters in height 2) Strictly follow recommended bay length for standards based on thescaffold material to be used, area and usage of scaffold structure 3) Strictly follow support / bracing recommendations based on the scaffold structural calculation 4) Scaffold Inspector to inspect the erected scaffold follows the scaffold plan strictly | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Scaffold collapse due to poor ground condition / poor soil bearing capacity | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect ground condition to be level, smooth and compact 2) Check soil bearing capacity based on soil classification 3) Replace soil if clay content is high and near the water table | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Scaffold collapse due to absence of proper base support | S | Physical / Property | 3 | 5 | 15 | B | 1) Conduct structural computation for scaffold structure more than 10 meters in height 2) Follow wood float / mud sill placement for the scaffold base 3) Ensure a leveled base and keep kicker lift height below 10cm or as close to the ground | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Scaffold collapse due to insufficient support / bracing | S | Physical / Property | 3 | 5 | 15 | B | 1) Conduct structural computation / calculation for scaffold structure more than 10 meters in height 2) Strictly follow recommended bay length for standards based on thescaffold material to be used, area and usage of scaffold structure 3) Strictly follow support / bracing recommendations based on the scaffold structural calculation 4) Scaffold Inspector to inspect the erected scaffold follows the scaffold plan strictly | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Scaffold Construction | Scaffold collapse due to unsafe connection of scaffold components | S | Physical / Property | 2 | 4 | 8 | C | 1) Check the connection of scaffold materials 2) Check the quality of scaffold materials used | Sunyup Moon | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Collision between pumpcrete / transit mixer with other site vehicle due to absence of flagman | S | Physical / Property | 3 | 5 | 15 | B | 1) Conduct safety check before use of construction vehicles 2) Install safety device for construction vehicle and place the signal man | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Collision between pumpcrete / transit mixer with existing site structure due to overspeeding / non observance of traffic rules | S | Physical / Property | 3 | 4 | 12 | B | 1) Vehicle follow 20 kph speed limit 2) Vehicle pass at designated road | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Collision between transit mixer to pumpcrete while reversing due to absence of LED torch baton used by flagman at night | S | Physical / Property | 3 | 4 | 12 | B | 1) Assign trained flagman equipped with LED torch baton 2) Provide sufficient lighting during night works activity | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Collision between transit mixer to pumpcrete while reversing due to absence wood stopper | S | Physical / Property | 3 | 4 | 12 | B | 1) Install wood stopper to prevent run-off of dump truck 2) Inspect equipment before use to ensure brakes are properly working | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Site personnel struck by pumpcrete / transit mixer | S | Physical | 2 | 5 | 10 | B | 1) Provide pedestrian acecss for site personnel 2) Wear personal protective equipment | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Overturning of pumpcrete / transit mixer caused by bad ground condition | S | Property | 3 | 3 | 9 | C | 1) Flat and smooth ground 2) Potholes, uneven surface immediately covered | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Concrete falling from transit mixer chute due to improper rotation of drum | S | Environmental | 3 | 3 | 9 | C | 1) Check or inspect rotation of transit mixer drum 2) Provide concrete bag at the end of the transit mixer chute | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Transit mixer overturning when manoeuvring due to over rotation of drum | S | Property | 2 | 3 | 6 | C | 1) Check or inspect rotation of transit mixer drum 2) All vehicle / equipment to follow imposed speed limit, 20KPH | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Overturning / tumbling of pumpcrete due to collapse of outrigger when setting up on soft ground | S | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Overturning / tumbling of pumpcrete due to failure to fully extend its outriggers | S | Physical / Property | 2 | 4 | 8 | C | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Check and ensure outrigger are fully extended | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Overturning of pumpcrete due to ground settlement of out-rigger's support during operation | S | Physical / Property | 3 | 4 | 12 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Check the ground settlement of outrigger support during setting-up of pumpcrete 4) Barricade the perimeter of the pumpcrete and prohibit entry through strict supervision | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Setting up of pumpcrete prior to concreting works | Overturning of pumpcrete after setting too close to excavation edge | S | Physical / property | 3 | 4 | 12 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Inspect the ground condition, provide steel plate on unstable or backfilled area 3) Check the ground settlement of outrigger support during setting-up of pumpcrete 4) Set outriggers at least 2 meters from the edge of excavation area 5) Assign 3rd party certified & competent pumpcrete operator | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Using uninspected power tools | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect and check power tools before using 2) Check if machine guarding and auxiliary handle available | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Using power tools with frayed / damage extension cable | S | Physical / Property | 3 | 5 | 15 | B | 1) Check power tools extension cable for posssible damage / defect 2) Inspect cable connection to the power tool and male socket | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Electric shock caused by inadequate insulation and absence of ELCB | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect if cable is 3-phase or double insulated 2) Check power source if provided with 30mA ELCB 3) Inspect if electrical DB is properly grounded | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Hand injury due to improper use of chipping gun | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if personnel is competent to use the chipping gung 2) Check proper handling and use of power tools by worker | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Concrete debris getting into the eye due fo absence of proper PPE | S | Health | 3 | 4 | 12 | B | 1) Personnel must wear safety goggles / full face shield 2) Lower the pumpcrete hose as much as possible to prevent splash | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Skin allergy caused by exposure to cement or concrete product | S | Hralth | 3 | 4 | 12 | B | 1) Personnel must wear proper PPE such as disposable coverall, gum boots, rubber gloves, etc. 2) Check all personnel PPE before allowing them to work | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Fall on the same level due to poor management of cables / poor housekeeping | S | Physical | 3 | 5 | 15 | B | 1) Conduct regular housekeeping and remove waste / unwanted materials 2) Arrange electrical cable by hanging overhead using insulated S-bar or cable posts | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Back / hand / body pain due to repititive movement | S | Physical | 3 | 3 | 9 | C | 1) Assign buddy system to prevent prolong use of power tool 2) Provide frequent breaks to break monotony of movement | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Overturning due to bad condition of scaffold structure | S | Physical | 3 | 5 | 15 | B | 1) Scaffold Inspector to inspect the scaffold structure before use 2) Wear and use full body harness | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Concrete debris falling to personnel while maneuvering the pumpcrete hose | S | Physical | 3 | 5 | 15 | B | 1) TBT prior to concreting and remind worker to keep away from the pumpcrete hose 2) Wear personal protective equipment (safety helmet, gum boots, etc.) | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel struck by pumpcrete hose during concrete pouring | S | Physical | 3 | 5 | 15 | B | 1) Assign experienced workers to hold the pumpcrete hose 2) Use pp rope as guide rope or tagline connected to pumpcrete hose to minimize contact 3) Inspect controls of pumpcrete if in good working condition | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel struck by concrete debris after rupture of concrete hose | S | Physical | 3 | 5 | 15 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Assign 3rd party certified & competent pumpcrete operator 3) Conduct inspection of equipment prior to use using checklist 4) Remind workers to keep away from the boom of pumpcrete | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel struck by pumpcrete pipe after joint connection is dislodged | S | Physical | 3 | 5 | 15 | B | 1) Inspect the equipment & its documents and provide operation permit if permitted to work 2) Assign 3rd party certified & competent pumpcrete operator 3) Conduct inspection of equipment prior to use using checklist 4) Remind workers to keep away from the boom of pumpcrete | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall caused by not wearing safety harness | S | Physical | 3 | 5 | 15 | B | 1) Wear & use full body harness with 2 lanyards 2) Comply with 100% tie-off 3) Before height work, practice double hook demonstration 4) Workers must attend Work at Heights safety training | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall due to absence of safety rail and safety belt | S | Physical | 3 | 2 | 6 | C | 1) Install standard height guard rail / safety rail on all sides 2) Wear and use full body harness when working on mobile scaffold | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall due to absence of appropriate access ladder | S | Physical | 3 | 2 | 6 | C | 1) Install the necessary access ladder leading to the working platform of the mobile scaffold | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall due to absence of proper working platform | S | Physical | 3 | 4 | 12 | B | 1) Avoid using straight ladder as working platform and made of wood 2) use step / A-type ladder of approved materials 3) Check step ladder condition before use and assign worker to hold | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall from moving along the elevated area | S | Physical | 3 | 5 | 15 | B | 1) Install safety rail on the edge 2) Wear full body hanress and install lifeline to tie-off | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall while stepping on damaged platform | S | Physical | 2 | 4 | 8 | C | 1) Check safety condition of platform before use 2) Personnel to wear full body harness and follow 100% tie-off policy | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personel fall when lifeline being used is unhinged | S | Physical | 2 | 5 | 10 | B | 1) Check and daily inspect lifeline condition and restraining condition 2) Check anchorage points of lifeline | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall while working on the cantilever scaffold with wide gap from the wall | S | Physical | 2 | 5 | 10 | B | 1) Tie-off lanyards of full body harness to an auxiliary lifeline 2) Secure lifeline properly and regularly check its condition | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall while leaning over the safety rail | S | Physical | 3 | 3 | 9 | C | 1) Install the safety rail properly 2) Wear full body harness and follow 100% tie-off policy | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall due to absence of appropriate access ladder | S | Physical | 3 | 2 | 6 | C | 1) Install the necessary access ladder leading to the working platform of the mobile scaffold | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall from ladder while carrying tools / materials | S | Physical / Property | 3 | 4 | 12 | B | 1) Maintain 3-point contact when climbing a ladder 2) Do not carry tools / materials by hand when climbing the ladder 3) Use belt bags to strap hand tools | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall on the same level due to poor management of cables / poor housekeeping | S | Physical | 3 | 5 | 15 | B | 1) Conduct regular housekeeping and remove waste / unwanted materials 2) Arrange electrical cable by hanging overhead using insulated S-bar or cable posts | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall on the same level when stepping over the steel rebar | S | Physical | 3 | 5 | 15 | B | 1) Provide wood planks as temporary access across the rebar matting 2) Install rebar cap to protruding rebar used as guide for concrete level | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Personnel fall because of absence of cover at openings | S | Physical | 3 | 4 | 12 | B | 1) Install cover on all floor opening and safety guard to prevent falling 2) Provide appropriate safety / warning signage | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Concrete pouring | Soil pollution due to spill of slurry concrete on the ground | S | Environmental | 2 | 4 | 8 | C | 1) Provide secondary containment / drip tray to contain slurry concrete from contaminating the ground soil 2) Conduct regular housekeeping and removed hardened plaster mix | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Using uninspected equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Inspect and check equipment (one bagger mixer) before using 2) Check if machine guarding for rotating parts installed | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Caught in / entanglement because of carelessness when placing materials on drum of mixer | S | Physical | 2 | 3 | 6 | C | 1) Exercise caution and avoid wearing loose clothing / safety gloves when placing plastering materials on the drum of mixer 2) Isolate mixing area and maintain safe distance when equipment is mixing the plaster mix | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Tumbling / slip of worker due to improper use of equipment | S | Physical | 1 | 3 | 3 | D | 1) Assign trained worker to operate equipment 2) Check emergency stop button of equipment before use | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Eye splash of chemical during mixing | S | Physical | 1 | 4 | 4 | D | 1) Follow instructions based on MSDS 2) Wear Personal protective equipment / full face shield 3) Provide emergency eye wash at the work area | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Fall on the same floor due to scattered materials | S | Physical | 3 | 3 | 9 | C | 1) Conduct housekeeping and remove loose materials from the ground | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Soil pollution due to spill of concrete mix on the ground | S | Environmental | 2 | 4 | 8 | C | 1) Provide secondary containment / drip tray to contain slurry concrete from contaminating the ground soil 2) Conduct regular housekeeping and removed hardened plaster mix | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Mixing of cement plaster | Breathing difficulty after inhaling cement dust when placing / mixing the plaster in the equipment | S | Physical / Health | 3 | 4 | 12 | B | 1) Provide and use dust mask / cartridge mask 2) Isolate mixing area and maintain safe distance during placing of materials and mixing | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Overturning due to bad condition of scaffold structure | S | Physical | 3 | 5 | 15 | B | 1) Scaffold Inspector to inspect the scaffold structure before use 2) Wear and use full body harness | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Hazard of overturning due to narrow platform | S | Physical / Property | 3 | 3 | 9 | C | 1) Working platform width minimum of 60cm 2) Maintain secured and full planking working platform | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Eye damage because of absence of personal protective equipments | S | Physical | 2 | 4 | 8 | C | 1) Wear safety goggles or full face shield | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Respiratory disease caused by scattered dust / inadequate ventilation | S | Physical / Health | 2 | 4 | 8 | C | 1) Provide enough ventilation / exhaust in the workplace 2) Wear and use dust mask or cartidge filter mask | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Tumbling and collision between worker due to insufficient lighting | S | Physical | 2 | 3 | 6 | C | 1) Provide enough lighting with more than 60 Lux illumination at the work site | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Overturning / personnel fall due to sudden movement of mobile scaffold for failure to lock caster wheels | S | Physical / Property | 3 | 3 | 9 | C | 1) Check safety condition of mobile scaffold before use 2) Inspect and check if caster wheels of mobile scaffold are locked | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Overturning due to absence of adequate support / bracing for mobile scaffold | S | Physical / Property | 3 | 2 | 6 | C | 1) Install the necessary diagonal bracing support for the mobile scaffold 2) Install plan bracing to prevent twisting of mobile scaffold | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Overturning due of absence of outrigger on mobile scaffold | S | Physical / Property | 3 | 1 | 3 | D | 1) Install appropriate ourigger supprot to prevent overturning 2) Install safety alarm device for overturning | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Overturning / personnel fall due to sudden movement of mobile scaffold for failure to lock caster wheels | S | Physical / Property | 3 | 3 | 9 | C | 1) Check safety condition of mobile scaffold before use 2) Inspect and check if caster wheels of mobile scaffold are locked | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Material fall while moving during plastering work | S | Physical | 3 | 5 | 15 | B | 1) Distance of platform from edge within 20cm 2) Install complete planking of platform without gap | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Material fall due excessive storing of materials on the platform | S | Property | 3 | 4 | 12 | B | 1) Install safety rail and toe board along the platform edge 2) Install safety net for additional fall prevention 3) Avoid storing excessive amount / quantity of materials on the platform | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Material fall caused by rope snapping while lifting the bucket of mortar | S | Physical / Property | 2 | 4 | 8 | C | 1) Check the PP rope before use | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Material fall because because of absence of toe board on scaffold platform | S | Physical / Property | 2 | 2 | 4 | D | 1) Install toe board on all platform edges 2) Install additional safety net if practicable | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall due to unsafe installation of fall prevention facility | S | Physical / Property | 3 | 5 | 15 | B | 1) Install safe, secure and appropriate height safety rail 2) Secure material properly from the platform 3) Wear and tie-off the full body harness | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall from moving along the elevated area | S | Physical | 3 | 5 | 15 | B | 1) Install safety rail on the edge 2) Wear full body hanress and install lifeline to tie-off | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall while leaning over the safety rail | S | Physical | 3 | 3 | 9 | C | 1) Install the safety rail properly 2) Wear full body harness and follow 100% tie-off policy | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall while stepping on damaged platform | S | Physical | 2 | 4 | 8 | C | 1) Check safety condition of platform before use 2) Personnel to wear full body harness and follow 100% tie-off policy | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personel fall when lifeline being used is unhinged | S | Physical | 2 | 5 | 10 | B | 1) Check and daily inspect lifeline condition and restraining condition 2) Check anchorage points of lifeline | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall while working on the cantilever scaffold with wide gap from the wall | S | Physical | 2 | 5 | 10 | B | 1) Tie-off lanyards of full body harness to an auxiliary lifeline 2) Secure lifeline properly and regularly check its condition | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall from ladder scaffold and mobile ladder | S | Physical | 3 | 3 | 9 | C | 1) Check the condition of the access ladder 2) Install the appropriate access ladder for the mobile scaffold 3) Working platform fully planked and opening covered | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall caused by unsafe condition of locking and strength of mobile scaffold | S | Physical | 3 | 2 | 6 | C | 1) Fix platform tightly on mobile scaffold 2) Wear and use full body harness 3) Check lock of caster wheels are engaged | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall from mobile scaffold when moved while working | S | Physical | 3 | 2 | 6 | C | 1) Do not move mobile scaffold while personnel are working or on top of the mobile scaffold | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall due to absence of appropriate access ladder | S | Physical | 3 | 2 | 6 | C | 1) Install the necessary access ladder leading to the working platform of the mobile scaffold | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall from ladder while carrying tools / materials | S | Physical / Property | 3 | 4 | 12 | B | 1) Maintain 3-point contact when climbing a ladder 2) Do not carry tools / materials by hand when climbing the ladder 3) Use belt bags to strap hand tools | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Plastering work | Personnel fall on the same level due to poor management of cables / poor housekeeping | S | Physical | 3 | 5 | 15 | B | 1) Conduct regular housekeeping and remove waste / unwanted materials 2) Arrange electrical cable by hanging overhead using insulated S-bar or cable posts | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material fall caused by improper / unsafe handling of material while using crane | S | Physical / Property | 3 | 4 | 12 | B | 1) Check safe lifting requirement for materials more than 10tons weight 2) Check safety condition of equipment / lifting gears before use 3) Lifting work should be conducted by 3rd party certified personnel | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material fall due to unsecured load and no proper lashing | S | Physical / Property | 2 | 5 | 10 | B | 1) Materials placed on rack or box and tied 2) Materials secured with lashing belt | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material fall caused by improper / unsafe stacking | S | Physical / Property | 2 | 3 | 6 | C | 1) Keep materials separately, Don't pile more than 1.5m 2) Install safety device (wood wedge) for rolling materials 3) Keep materials inside packing box / racks | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Material / Equipment fall due to unsecured loading and exceeding load capacity | S | Property | 2 | 5 | 10 | B | 1) Conduct inspection of materials more than 10 Tons in weight 2) Lifting to be conducted by 3rd party certified crane operator/ rigger 3) Use appropriate equipment to unload materials 4) Crane outrigger fully extended and equipment set on stable / smooth ground 5) Materials properly lashed & secure before lifting | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collision between transport vehicle with existing site structure due to overspeeding / non observance of traffic rules | S | Property | 3 | 4 | 12 | B | 1) Vehicle follow 20 kph speed limit 2) Vehicle pass at designated road | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Overturning of transport vehicle caused by bad ground condition | S | Property | 3 | 3 | 9 | C | 1) Flat and smooth ground 2) Potholes, uneven surface immediately covered | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Overturning because workers failed to conduct housekeeping at the workplace | S | Physical / Property | 1 | 2 | 2 | E | 1) Conduct safety inspection for materials more than 10 Tons in weight 2) Check equipment safety condition using chesklit before use 3) Lifting work should be conducted by trained worker 4) Use 3rd party certified material box 5) Check the safety condition of all ligting gears / tackles 6) Conduct regualr housekeeping at the workplace | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Collision of equipment / vehicle due to inconsistent traffic signages | S | Physical / Property | 2 | 2 | 4 | D | 1) Standardizeall traffic / safety signage at the work site 2) Assign trained flagman for every equipment | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | In and Out of materials | Site personnel struck by transport vehicle | S | Physical | 2 | 5 | 10 | B | 1) Provide pedestrian acecss for site personnel 2) Wear personal protective equipment | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Personnel falling because of absence of safety rail around the excavation | S | Physical | 3 | 5 | 15 | B | 1) Install appropriate hard safety rail along the excavation perimeter | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Personnel fall while inspecting along the excavation edge | S | Physical | 2 | 3 | 6 | C | 1) Wear personal protective equipments 2) Install safety rail along the edge of excavation | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Personnel fall / tumble due to absence of safe pathway | S | Physical | 2 | 4 | 8 | C | 1) Provide proper temporary access with hand rails 2) Remove obstruction from the access way | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Survey and Inspection | Collapse caused by inadequate investigation of geological features | S | Physical / Property | 2 | 4 | 8 | C | 1) Follow and comply proper side sloping based on soil classification 2) Install the earth dike / berm and safety net against soil erosion 3) Check safety condition for slope with earth anchor and shotcrete 4) Investigate the soil condition in the work site | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Retaining Wall | Cut / laceration due to carelessness in using the circular saw | S | Physical | 3 | 4 | 12 | B | 1) Don't use the circular saw for woods 2) Use the automatic circular saw 3) Install automatic sensor/emergency stop device | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Retaining Wall | Collapse of excavation arises due to failure to support wall during excavation | S | Physical / Property | 3 | 4 | 12 | B | 1) Install vertical board for every 1.5m deep when excavating soft soil 2) Reinforce the vertical / poling board with adequate support | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Retaining Wall | Excavation wall collapse due to failure to regularly check the geological features | S | Physical / Property | 3 | 4 | 12 | B | 1) Immediately Work stop 2) Check and modify the method of construction based on the current soil / ground condition | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Retaining Wall | Falling because of absence of safety rail | S | Physical | 2 | 4 | 8 | C | 1) Install appropriate hard safety rail along the excavation perimeter | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Collapse of excavation wall during installation of the sheathing board | S | Physical / Property | 3 | 3 | 9 | C | 1) Comply with standards for sloping requirement for excavation based on soil classificiation 2) Follow safe work methodology of construction and provide dewatering activity if needed 3) Check compliance through survey | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Collapse of excavation wall caused by deformation of H-BEAM and sheathing board | S | Physical / Property | 3 | 3 | 9 | C | 1) Measure and check the ground water level and earth pressure 2) Reinforce the center pile plate and areas where visual deformity on the shoring sheet is observed | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Collapse of excavation wall due to change in earth pressure caused by discharge of underground water | S | Physical / Property | 2 | 3 | 6 | C | 1) Comply with standards for sloping requirement for excavation based on soil classificiation 2) Follow safe work methodology of construction and provide enough dewatering equipment 3) Regularly check excavation / dewatering condition | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Collapse of backfill materials due to subsidence of mud and sand in the area | S | Physical / Property | 2 | 3 | 6 | C | 1) Follow safe work methodology for backfilling activity 2) Regularly check the site condition | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Collapse of excavation wall and shoring caused by unsafe and improper construction | S | Physical / Property | 2 | 3 | 6 | C | 1) Follow and comply with regulations of lay out and based on structural design & review 2) Set stiffener support on regular intervals | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Collapse caused by excessive stacking of materials | S | Physical / Property | 2 | 2 | 4 | D | 1) Avoid stockpiling materials along the retaining wall 2) Immediately remove unwanted materials along the excavation edge | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Collapse caused by increased / excessive earth pressure | S | Physical / Property | 2 | 4 | 8 | C | 1) Comply with standards for sloping requirement for excavation based on soil classificiation 2) Follow safe work methodology of construction and provide enough dewatering equipment 3) Regularly check excavation / dewatering condition | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Collapse of excavation due to uncontrolled groundwater | S | collapse | 4 | 5 | 20 | A | 1) Comply with standards for sloping requirement for excavation based on soil classificiation 2) Follow safe work methodology of construction and provide enough dewatering equipment 3) Regularly check excavation / dewatering condition | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Overturning of equipment due to unstable / backfilled ground for equipment | S | Physical / Property | 4 | 5 | 20 | A | 1) Ensure stable, compact and level ground 2) Use metal plate if equipment is set up on backfilled ground | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Overturning due to carelessness when lifting the H-Beam | S | Physical / Property | 2 | 3 | 6 | C | 1) Use equipment inspected / approved by Doosan and 3rd party certified 2) Check the safety condition of the lifting gears / tackles 3) 3rd party certified crane operator / rigger to be utilized | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Fall and collapse during dismantling of the sheathing board | S | Physical / Property | 2 | 3 | 6 | C | 1) Comply with standards for sloping requirement of excavation based on soil classificiation 2) Follow safe work methodology of construction and provide dewatering activity if required 3) Check compliance through survey | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Personnel fall while working on the upper part of the sheathing board | S | Physical | 3 | 3 | 9 | C | 1) Install safety Fixed rail and safety net as fall prevention 2) Wear and use the necessary personal protective equipments | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Personnel fall because of absence of safety rail | S | Physical | 3 | 3 | 9 | C | 1) Install safety rail and safety net as fall prevention | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Fall and collision because H-Beam cut off the wire rope during lifting | S | Physical | 3 | 3 | 9 | C | 1) Check safe lifting requirement for materials more than 10tons weight 2) Check safety condition of equipment / lifting gears before use 3) Lifting work should be conducted by 3rd party certified personnel | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Fall and collision caused when wire rope is cut during dismantling of the temporary structure | S | Physical / Property | 1 | 5 | 5 | C | 1) Check safe lifting condition for materials more than 10tons in weight 2) Check safety condition of equipment before use 3) Ensure 3rd party certified operator / rigger conduct the lifting | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Fall and collision due to unstable ground condition and crane outrigger not locked | S | Physical / Property | 3 | 2 | 6 | C | 1) Check safe lifting requirement for materials more than 10tons weight 2) Check safety condition of equipment / lifting gears before use 3) Lifting work should be conducted by 3rd party certified personnel 4) Ensure crane is set-up on stable, level and compacted ground 5) Ensure crane outriggers fully extended and locking pin engaged | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Subsidence of sand due to uncontrolled underground water | S | Physical / Property | 2 | 3 | 6 | C | 1) Follow safe work methodology of construction and provide / conduct dewatering activity | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Electric shock because of absence of automatic shock protector when using the welding machine | S | Physical | 2 | 4 | 8 | C | 1) Set automatic shock protector on A/C arc welder 2) Check and ensure all live parts are properly insulated or covered | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Hand and backache due to unsafe / improper handling of materials | S | Physical | 2 | 3 | 6 | C | 1) Ensure two-person team during manual handling of materials 2) Allow workers to carry less than 25 kilos of weight only | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Foreign particles getting into the eye during boring activity | S | Physical | 2 | 3 | 6 | C | 1) Use safety glasses / goggles | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Shoring Installation | Burn caused by carelessness while handling the gas cutting equipment | S | Physical | 2 | 2 | 4 | D | 1) Attach the flashback arrestor for the gas cutting equipment 2) Only trained and competent personnel to perform activity | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Sheet Piling Works | Collision between equipment or vehicle due to absence of flagman with the equipment or other site vehicle / equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Install safety / trafic signage 2) Install safety device for vehicle and assign flagman / banks man | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Sheet Piling Works | Collapse of excavation due to absence of safety net and improper side slope | S | Physical / Property | 3 | 4 | 12 | B | 1) Check excavation integrity and side slope to conform with MS 2) Install safety net along excavation slope or provide retaining wall | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Sheet Piling Works | Personnel fall due to absence of safety rail along perimeter of excavation | S | Physical | 3 | 5 | 15 | B | 1) Install appropriate hard safety rail along the excavation perimeter | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Sheet Piling Works | Personnel fall caused by carelessness of workers and insufficient lighting | S | Physical | 2 | 5 | 10 | B | 1) Provide enough lighting with more than 60 Lux illumination at the work site | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Sheet Piling Works | Overturning of equipment / vehicle caused by insufficient traffic / safety signage entering / exiting the area | S | Physical / Property | 2 | 5 | 10 | B | 1) Inspect equipment / vehicle before start of activity 2) Install safety device for construction equipment / vehicle and assign flagman / banks man 3) Install the earth dike or earth mound | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Sheet Piling Works | Overturning of equipment caused by multi tasking activity | S | Physical / Property | 2 | 3 | 6 | C | 1) Avoid multitasking of equipment during piling work | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Sheet Piling Works | Overturning due to noncompliance with regulations and safety device | S | Property | 2 | 3 | 6 | C | 1) Keep materials separately, Don't pile more than 1.5m 2) Install safety device (wedge) for unloading and rolling materials | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Sheet Piling Works | Electric shock caused by carelessness in using welding machine, electric motor and motor pump. | S | Physical | 3 | 4 | 12 | B | 1) Use proper socket and plug with grounding and 3 Phase electrical cable 2) Connect extension cable on electrical DB with 30mA ELCB / RCB / GFCI | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Sheet Piling Works | Physical injury due to rupture of underground pressurized pipeline | S | Physical | 1 | 3 | 3 | D | 1) Check and verify location of undergounrd utilities 2) Use manual excavation instead of using excavation equipment | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Material fall due improper & unsafe handling / tranport | S | Physical / Property | 3 | 5 | 15 | B | 1) Secure materials properly before transporting with lashing belt 2) Provide safety net cover to prevent material fall | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Material fall due to carelessness in using the lifting rope | S | Property | 3 | 4 | 12 | B | 1) Check the lifting device for damage, defect and wear 2) Immediately remove or quarantine damaged lifting device / gears | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Collision due to inexperienced and unlicensed driver | S | Physical / Property | 3 | 5 | 15 | B | 1) Check driver's license before allowing personnel to drive vehicle 2) Check vehicle safety before driving using BLOWBAG | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Collision during unsafe reversing of construction equipment / vehicle | S | Physical / Property | 3 | 5 | 15 | B | 1) Check equipment / vehicle safety using checklist / BLOWBAG before use 2) Install reverse / collision alarm of equipment and assign flagman 3) Install earth dike / mound along excavation edge | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Personnel fall due to absence of safety rail along perimeter of excavation | S | Physical | 3 | 5 | 15 | B | 1) Install appropriate hard safety rail along the excavation perimeter | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Personnel fall caused by carelessness of workers and insufficient lighting | S | Physical | 2 | 5 | 10 | B | 1) Provide enough lighting with more than 60 Lux illumination at the work site | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Overturning / tumbling of worker during reversing of excavator | S | Physical / Property | 3 | 5 | 15 | B | 1) Install reverse alarm and assign trained flagman 2) Ensure slope is gradual and remove obstructions from access | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Electric shock caused by carelessness in using welding machine, electric motor and motor pump. | S | Physical | 3 | 4 | 12 | B | 1) Use proper socket and plug with grounding and 3 Phase electrical cable 2) Connect extension cable on electrical DB with 30mA ELCB / RCB / GFCI | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Electric shock due to carelessness during the repair of pump | S | Physical | 2 | 4 | 8 | C | 1) Ensure pump is powered off before conducting any repair 2) Check cable / cable connections and ensure pump body grounding | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Electrocution / electrical shock due to frayed / damaged electrical wire | S | Physical | 2 | 4 | 8 | C | 1) Check extension cables for frayed, damaged or exposed wire 2) Use proper socket and plug with grounding and 3 Phase electrical cable | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Fire / explosion arise as a result of carelessness at storage for compressed gas cylinders | S | Physical / Property | 1 | 5 | 5 | C | 1) Follow doosan guidelines for the proper storage of compressed gas cylinders at site 2) Strictly comply with the safety requirements for HAZMAT 3) Ensure all gas cylinders are properly capped and secured with metal chain | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Overturning / fall of equipment due to misuse | S | Physical / Property | 3 | 4 | 12 | B | 1) Check equipment safety using checklist / BLOWBAG before use 2) Use equipment as per manufacturers recommendation | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
false | Common | Overturning / fall of equipment caused by inadequate checking of equipment | S | Physical / Property | 2 | 3 | 6 | C | 1) Ensure equipment is inspected by Doosan and operation permit is attached 2) Conduct daily inspection of equipment using appropriate checklist | Yunchil Kim | 2024-01-31 | 1 | 1 | 1 | E
삭제 Del | 작업활동 및 내용 Work & Contents | 유해위험요인 및 환경측면 영향 Hazard & Risk | EHS | 피해형태 및 환경영향 Damage & Effect | 빈도 Risk Rate | 강도 Severity | T | 등급 Rate | 개선대책 및 세부관리방안 Corrective Action | 개선담당자 Responsibility | 개선일자 Action Date | 빈도 Likelihood | 강도 Severity | T | 등급 Rate
false | Vessel mobilization to Site | Capsizing / running aground due to poor weather / sea condition | S | Physical / Property | 3 | 5 | 15 | B | 1) Monitor regularly the weather forecast 2) Check navigational charts / aids to be current 3) Plan voyage using the shortest route | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Capsizing / running aground due to failure of on board navigation equipment | S | Physical / Property | 2 | 5 | 10 | B | 1) Check tugboat condition, mechanical / electrical equipment 2) Check navigational instruments & communication equipment | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Capsizing / running aground due to poor seamanship | S | Physical / Property | 2 | 5 | 10 | B | 1) Boat Captain must have valid license, seamans book, SOLAS, etc. 2) All crew must have valid seamans book, SOLAS, etc. | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Water entering vessel compartment during voyage | S | Physical / Property | 3 | 5 | 15 | B | 1) Close all hatches, portholes and ensure water tightness 2) Check bilge pumps to be in good working condition | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Environmental pollution for disposing bilge / waste during voyage | E | Environmental | 3 | 5 | 15 | B | 1) No waste must be disposed within 12 nautical miles from the nearest shoreline 2) No HME garbage / waste must be disposed to the sea | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Man falling overboard while loitering on deck during voyage | S | Physical | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during the voyage 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Unsecured material falling overboard during voyage / rough sea condition | S | Property | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Vessel running aground due to improper mooring / slack on mooring line | S | Physical / Property | 3 | 5 | 15 | B | 1) Regularly check slack / taut of mooring lines 2) Tugboat to standby alongside barge at all times | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Vessel running aground / drifting from station due to rough sea condition | S | Physical / Property | 3 | 5 | 15 | B | 1) Monitor regularly the weather forecast 2) Regularly check vessel stationing specially when anchored 3) Suspend activity if waves more than 1.5 meters high, wind speed more than 10 m/s and visibility less than 1Km | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Vessel running aground / drifting from station due to failure of tug boat | S | Physical / Property | 3 | 5 | 15 | B | 1) Check tugboat condition, mechanical / electrical equipment 2) Conduct regular maintenance of tug boat | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Snapping of mooring line during rough sea condition / during towing of barge | S | Physical / Property | 3 | 5 | 15 | B | 1) Monitor regularly the weather forecast 2) Regularly check slack / taut of mooring lines 3) Use appropriate size of mooring line and check its condition 4) Tugboat to standby alongside barge at all times 5) Assign anchor / mooring detail watch | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Vessel sustaining damage from collision between barge and tug boat due to rough sea condition | S | Physical / Property | 3 | 5 | 15 | B | 1) Provide sufficient number of fenders between barge and tug boat 2) Anchor barge separately from other vessel during high wave condition 3) Boat Captain to monitor the activity and assign competent weatchman | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Personnel struck by dislodged mooring blocks during towing of barge | S | Physical | 3 | 5 | 15 | B | 1) Check condition of chocks, cleats, bollard for defect / damage 2) Use appropriate size of mooring line and check its condition 3) Crew to stay inside vessel / bridge during towing operation | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Personnel slipping on the same level due to materials / slippery deck | S | Physical | 3 | 4 | 12 | B | 1) Maintain cleanliness on the deck 2) Immediately mop and dry wet deck surface | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Environmental pollution due to disposal of bilge / waste materials | S | Environmental | 3 | 5 | 15 | B | 1) No waste must be disposed within 12 nautical miles from the nearest shoreline 2) No HME garbage / waste must be disposed to the sea | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Environmental pollution due to accidental oil / fuel spillage | S | Environmental | 3 | 5 | 15 | B | 1) Store HAZMAT inside vessel compartment / paint locker 2) HAZMAT stored on deck must be properly lashed and with secondary containment 3) Regularly check secondary containment and remove accumulated oil 4) Provide emergency spill kit and regularly conduct drill | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Man falling overboard while working on deck | S | Physical | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during mooring / anchoring 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Unsecured material falling overboard during mooring / anchoring | S | Property | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Equipment striking vessel structure / crew due to incompetent operator / | S | Physical / Property | 3 | 5 | 15 | B | 1) Crane operator experienced and with 3rd party certificate | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Lost of clamshell when using damage / defective equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if crane possess valid 3rd party inspection certificate 2) Check crane condition before use using checklist | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Lost of drop chisel to sea due to breaking of wire rope | S | Property | 3 | 5 | 15 | B | 1) Check wire cable and connections 2) Check lifting tackles / safety pins | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Spread of turbid water to open sea due to absence of siltation boom | E | Envirojnmental | 3 | 5 | 15 | B | 1) Install siltation boom / silt skirt with silt curtain 2) Check conenctions between silt skirt and provide geo textile 3) Assign watchman to monitor turbidity generated by the activity | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Spread of turbid water to open sea due to damage silt curtain | E | Envirojnmental | 3 | 5 | 15 | B | 1) Regularly check condition of silt skirt and silt curtain 2) Immediately repair damaged silt curtain | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Vessel running aground due to rough sea condition / high waves | S | Physical / Property | 3 | 5 | 15 | B | 1) Regularly monitor the weather forecast 2) Assign anchor / mooring details to check anchor / mooring condition 3) Suspend activity if waves more than 1.5 meters high, wind speed more than 10 m/s and visibility less than 1Km | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Personnel slipping on the same level due to materials / slippery deck | S | Physical | 3 | 4 | 12 | B | 1) Maintain cleanliness on the deck 2) Immediately mop and dry wet deck surface | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Environmental pollution due to disposal of bilge / waste materials | E | Environmental | 3 | 5 | 15 | B | 1) No waste must be disposed within 12 nautical miles from the nearest shoreline 2) No HME garbage / waste must be disposed to the sea | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Environmental pollution due to accidental oil / fuel spillage | E | Environmental | 3 | 5 | 15 | B | 1) Store HAZMAT inside vessel compartment / paint locker 2) HAZMAT stored on deck must be properly lashed and with secondary containment 3) Regularly check secondary containment and remove accumulated oil 4) Provide emergency spill kit and regularly conduct drill | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Man falling overboard while working on deck | S | Property | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during operation 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Unsecured material falling overboard during activity | S | Property | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Equipment striking vessel structure / crew due to incompetent operator | S | Physical / Property | 3 | 5 | 15 | B | 1) Crane operator experienced and with 3rd party certificate | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Lost of clamshell when using damage / defective equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if crane possess valid 3rd party inspection certificate 2) Check crane condition before use using checklist | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Lost of clamshell bucket to sea due to breaking of wire rope | S | Property | 3 | 5 | 15 | B | 1) Check wire cable and connections 2) Check lifting tackles / safety pins | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Spread of turbid water to open sea due to absence of siltation boom | E | Envirojnmental | 3 | 5 | 15 | B | 1) Install siltation boom / silt skirt with silt curtain 2) Check conenctions between silt skirt and provide geo textile 3) Assign watchman to monitor turbidity generated by the activity | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Spread of turbid water to open sea due to damage siltation boom | E | Envirojnmental | 3 | 5 | 15 | B | 1) Regularly check condition of silt skirt and silt curtain 2) Immediately repair damaged silt curtain | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Dredging vessel running aground due to rough sea condition / high waves | E | Physical / Property | 3 | 5 | 15 | B | 1) Regularly monitor the weather forecast 2) Assign anchor / mooring details to check anchor / mooring condition 3) Suspend activity if waves more than 1.5 meters high, wind speed more than 10 m/s and visibility less than 1Km | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Personnel hit by equipment during operation | E | Physical | 2 | 5 | 10 | B | 1) Strictly control movement of crew during operation 2) Maintain 5 meter distance from working equipment 3) Assign or provide barriers / demarkation line at barge deck | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Personnel slipping on the same level due to materials / slippery deck | E | Physical | 3 | 4 | 12 | B | 1) Maintain cleanliness on the deck 2) Immediately mop and dry wet deck surface | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Environmental pollution due to disposal of bilge / waste materials | E | Environmental | 3 | 5 | 15 | B | 1) No waste must be disposed within 12 nautical miles from the nearest shoreline 2) No HME garbage / waste must be disposed to the sea | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Environmental pollution due to accidental oil / fuel spillage | E | Environmental | 3 | 5 | 15 | B | 1) Store HAZMAT inside vessel compartment / paint locker 2) HAZMAT stored on deck must be properly lashed and with secondary containment 3) Regularly check secondary containment and remove accumulated oil 4) Provide emergency spill kit and regularly conduct drill | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Man falling overboard while working on deck | E | Property | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during operation 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Unsecured material falling overboard during operation | E | Physical | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Equipment striking vessel structure / crew due to incompetent operator | E | Physical / Property | 3 | 5 | 15 | B | 1) Crane operator experienced and with 3rd party certificate | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Lost of clamshell when using damage / defective equipment | E | Physical / Property | 3 | 5 | 15 | B | 1) Check if crane possess valid 3rd party inspection certificate 2) Check crane condition before use using checklist | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Lost of clamshell bucket to sea due to breaking of wire rope | E | Property | 3 | 5 | 15 | B | 1) Check wire cable and connections 2) Check lifting tackles / safety pins | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Vessel running aground due to rough sea condition / high waves | E | Physical / Property | 3 | 5 | 15 | B | 1) Regularly monitor the weather forecast 2) Assign anchor / mooring details to check anchor / mooring condition 3) Suspend activity if waves more than 5 meters high, wind speed more than 10m/s and visibility less than 1 Km. | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Spread of turbid water to open sea due to absence of siltation boom | E | Envirojnmental | 3 | 5 | 15 | B | 1) Install siltation boom / silt skirt with silt curtain 2) Check conenctions between silt skirt and provide geo textile 3) Assign watchman to monitor turbidity generated by the activity | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Spread of turbid water to open sea due to damage siltation boom | E | Envirojnmental | 3 | 5 | 15 | B | 1) Regularly check condition of silt skirt and silt curtain 2) Immediately repair damaged silt curtain | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Personnel hit by equipment during operation | S | Physical | 2 | 5 | 10 | B | 1) Strictly control movement of crew during operation 2) Maintain 5 meter distance from working equipment | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Personnel slipping on the same level due to materials / slippery deck | S | Physical | 3 | 4 | 12 | B | 1) Maintain cleanliness on the deck 2) Immediately mop and dry wet deck surface | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Man falling overboard while working on deck | S | Property | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during operation 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Unsecured material falling overboard during mooring / anchorin | S | Physical | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Equipment striking vessel structure / crew due to incompetent operator | S | Physical / Property | 3 | 5 | 15 | B | 1) Crane operator experienced and with 3rd party certificate | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Overturning of crane barge due to rough sea condition | S | Physical / Property | 3 | 5 | 15 | B | 1) Suspend lifting operation if waves more than 1.5 meters high, wind speed more than 10m/s and visibility less than 1Km | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Fall of load due to defective lifting gears / lifting equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if crane possess valid 3rd party inspection certificate 2) Check crane condition before use using checklist 3) Check lifting gears and tackles before use | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Fall of load due to unsafe slinging | S | Physical / Property | 3 | 5 | 15 | B | 1) Use proper slinging & padding depending on the load 2) Use designated lifting lugs if available 3) Avoid lifting multiple materials of different configuration | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Fall of load due to improper signalling / incompetent rigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Only assign 3rd party certified rigger to give signal 2) Use radio or ensure hand signal is understood between rigger and crane operator | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) No personnel allowed under the load or crane boom 3) Clear deck of unwanted personnel during lifting operation | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Hitting other structure by load during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Diver hit by load while lowering the pipeline | S | Physical | 3 | 5 | 15 | B | 1) Divers to keep away from load when swinging pipe into place | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Man falling overboard while working on deck | S | Property | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during operation 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Unsecured material falling overboard during mooring / anchorin | S | Physical | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Diving Works | Drowning / suffering from decompression sickness due to human error | S | Physical | 3 | 5 | 15 | B | 1) Certified and competent divers only 2) Check divers physical and mental condition before each dive 3) Diving operations strictly controlled / supervised by Diving Foreman | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Diving Works | Drowning / suffering from decompression sickness due to equipment failure | S | Physical | 3 | 5 | 15 | B | 1) Check diving equipment and gears before use 2) Use pre-dive checklist before each diving activity | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Diving Works | Struck by suspended pipe during installation to the sea | S | Physical | 3 | 5 | 15 | B | 1) Divers to keep away from load when swinging pipe into place | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Diving Works | Drowning due to absence of buddy diver | S | Physical | 3 | 5 | 15 | B | 1) Maintain buddy system during diving activity 2) Check communication and visual equipment before each dive 3) Assign stand-by diver in case of emergency | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Equipment striking vessel structure / crew due to incompetent operator | S | Physical / Property | 3 | 5 | 15 | B | 1) Crane operator experienced and with 3rd party certificate | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Overturning of crane barge due to rough sea condition | S | Physical / Property | 3 | 5 | 15 | B | 1) Suspend lifting operation if waves more than 1.5 meters high, wind speed more than 10m/s and visibility less than 1Km | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Fall of load due to defective lifting gears / lifting equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if crane possess valid 3rd party inspection certificate 2) Check crane condition before use using checklist 3) Check lifting gears and tackles before use | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Fall of load due to unsafe slinging | S | Physical / Property | 3 | 5 | 15 | B | 1) Use proper slinging & padding depending on the load 2) Use designated lifting lugs if available 3) Avoid lifting multiple materials of different configuration | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Fall of load due to improper signalling / incompetent rigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Only assign 3rd party certified rigger to give signal 2) Use radio or ensure hand signal is understood between rigger and crane operator | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) No personnel allowed under the load or crane boom 3) Clear deck of unwanted personnel during lifting operation | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Hitting other structure by load during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Diver hit by load while lowering the pipeline | S | Physical | 3 | 5 | 15 | B | 1) Divers to keep away from load when swinging pipe into place | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Man falling overboard while working on deck | S | Property | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during operation 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Unsecured material falling overboard during mooring / anchorin | S | Physical | 4 | 5 | 20 | A | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E