## Sheet1
삭제 Del | 작업활동 및 내용 Work & Contents | 유해위험요인 및 환경측면 영향 Hazard & Risk | EHS | 피해형태 및 환경영향 Damage & Effect | 위험성 Risk Rate | 위험성 Risk Rate | 위험성 Risk Rate | 등급 Rate | 개선대책 및 세부관리방안 Corrective Action | 개선담당자 Responsibility | 개선일자 Action Date | 위험성 Risk Rate | 위험성 Risk Rate | 위험성 Risk Rate | 등급 Rate
삭제 Del | 작업활동 및 내용 Work & Contents | 유해위험요인 및 환경측면 영향 Hazard & Risk | EHS | 피해형태 및 환경영향 Damage & Effect | 빈도 Risk Rate | 강도 Severity | T | 등급 Rate | 개선대책 및 세부관리방안 Corrective Action | 개선담당자 Responsibility | 개선일자 Action Date | 빈도 Likelihood | 강도 Severity | T | 등급 Rate
false | Vessel mobilization to Site | Capsizing / running aground due to poor weather / sea condition | S | Physical / Property | 3 | 5 | 15 | B | 1) Monitor regularly the weather forecast 2) Check navigational charts / aids to be current 3) Plan voyage using the shortest route | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Capsizing / running aground due to failure of on board navigation equipment | S | Physical / Property | 2 | 5 | 10 | B | 1) Check tugboat condition, mechanical / electrical equipment 2) Check navigational instruments & communication equipment | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Capsizing / running aground due to poor seamanship | S | Physical / Property | 2 | 5 | 10 | B | 1) Boat Captain must have valid license, seamans book, SOLAS, etc. 2) All crew must have valid seamans book, SOLAS, etc. | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Water entering vessel compartment during voyage | S | Physical / Property | 3 | 5 | 15 | B | 1) Close all hatches, portholes and ensure water tightness 2) Check bilge pumps to be in good working condition | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Environmental pollution for disposing bilge / waste during voyage | E | Environmental | 3 | 5 | 15 | B | 1) No waste must be disposed within 12 nautical miles from the nearest shoreline 2) No HME garbage / waste must be disposed to the sea | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Man falling overboard while loitering on deck during voyage | S | Physical | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during the voyage 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Vessel mobilization to Site | Unsecured material falling overboard during voyage / rough sea condition | S | Property | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Vessel running aground due to improper mooring / slack on mooring line | S | Physical / Property | 3 | 5 | 15 | B | 1) Regularly check slack / taut of mooring lines 2) Tugboat to standby alongside barge at all times | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Vessel running aground / drifting from station due to rough sea condition | S | Physical / Property | 3 | 5 | 15 | B | 1) Monitor regularly the weather forecast 2) Regularly check vessel stationing specially when anchored 3) Suspend activity if waves more than 1.5 meters high, wind speed more than 10 m/s and visibility less than 1Km | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Vessel running aground / drifting from station due to failure of tug boat | S | Physical / Property | 3 | 5 | 15 | B | 1) Check tugboat condition, mechanical / electrical equipment 2) Conduct regular maintenance of tug boat | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Snapping of mooring line during rough sea condition / during towing of barge | S | Physical / Property | 3 | 5 | 15 | B | 1) Monitor regularly the weather forecast 2) Regularly check slack / taut of mooring lines 3) Use appropriate size of mooring line and check its condition 4) Tugboat to standby alongside barge at all times 5) Assign anchor / mooring detail watch | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Vessel sustaining damage from collision between barge and tug boat due to rough sea condition | S | Physical / Property | 3 | 5 | 15 | B | 1) Provide sufficient number of fenders between barge and tug boat 2) Anchor barge separately from other vessel during high wave condition 3) Boat Captain to monitor the activity and assign competent weatchman | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Personnel struck by dislodged mooring blocks during towing of barge | S | Physical | 3 | 5 | 15 | B | 1) Check condition of chocks, cleats, bollard for defect / damage 2) Use appropriate size of mooring line and check its condition 3) Crew to stay inside vessel / bridge during towing operation | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Personnel slipping on the same level due to materials / slippery deck | S | Physical | 3 | 4 | 12 | B | 1) Maintain cleanliness on the deck 2) Immediately mop and dry wet deck surface | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Environmental pollution due to disposal of bilge / waste materials | S | Environmental | 3 | 5 | 15 | B | 1) No waste must be disposed within 12 nautical miles from the nearest shoreline 2) No HME garbage / waste must be disposed to the sea | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Environmental pollution due to accidental oil / fuel spillage | S | Environmental | 3 | 5 | 15 | B | 1) Store HAZMAT inside vessel compartment / paint locker 2) HAZMAT stored on deck must be properly lashed and with secondary containment 3) Regularly check secondary containment and remove accumulated oil 4) Provide emergency spill kit and regularly conduct drill | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Man falling overboard while working on deck | S | Physical | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during mooring / anchoring 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Mooring / anchoring of vessel | Unsecured material falling overboard during mooring / anchoring | S | Property | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Equipment striking vessel structure / crew due to incompetent operator / | S | Physical / Property | 3 | 5 | 15 | B | 1) Crane operator experienced and with 3rd party certificate | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Lost of clamshell when using damage / defective equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if crane possess valid 3rd party inspection certificate 2) Check crane condition before use using checklist | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Lost of drop chisel to sea due to breaking of wire rope | S | Property | 3 | 5 | 15 | B | 1) Check wire cable and connections 2) Check lifting tackles / safety pins | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Spread of turbid water to open sea due to absence of siltation boom | E | Envirojnmental | 3 | 5 | 15 | B | 1) Install siltation boom / silt skirt with silt curtain 2) Check conenctions between silt skirt and provide geo textile 3) Assign watchman to monitor turbidity generated by the activity | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Spread of turbid water to open sea due to damage silt curtain | E | Envirojnmental | 3 | 5 | 15 | B | 1) Regularly check condition of silt skirt and silt curtain 2) Immediately repair damaged silt curtain | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Vessel running aground due to rough sea condition / high waves | S | Physical / Property | 3 | 5 | 15 | B | 1) Regularly monitor the weather forecast 2) Assign anchor / mooring details to check anchor / mooring condition 3) Suspend activity if waves more than 1.5 meters high, wind speed more than 10 m/s and visibility less than 1Km | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Personnel slipping on the same level due to materials / slippery deck | S | Physical | 3 | 4 | 12 | B | 1) Maintain cleanliness on the deck 2) Immediately mop and dry wet deck surface | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Environmental pollution due to disposal of bilge / waste materials | E | Environmental | 3 | 5 | 15 | B | 1) No waste must be disposed within 12 nautical miles from the nearest shoreline 2) No HME garbage / waste must be disposed to the sea | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Environmental pollution due to accidental oil / fuel spillage | E | Environmental | 3 | 5 | 15 | B | 1) Store HAZMAT inside vessel compartment / paint locker 2) HAZMAT stored on deck must be properly lashed and with secondary containment 3) Regularly check secondary containment and remove accumulated oil 4) Provide emergency spill kit and regularly conduct drill | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Man falling overboard while working on deck | S | Property | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during operation 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Drop Chiseling / Breaking of corals | Unsecured material falling overboard during activity | S | Property | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Equipment striking vessel structure / crew due to incompetent operator | S | Physical / Property | 3 | 5 | 15 | B | 1) Crane operator experienced and with 3rd party certificate | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Lost of clamshell when using damage / defective equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if crane possess valid 3rd party inspection certificate 2) Check crane condition before use using checklist | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Lost of clamshell bucket to sea due to breaking of wire rope | S | Property | 3 | 5 | 15 | B | 1) Check wire cable and connections 2) Check lifting tackles / safety pins | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Spread of turbid water to open sea due to absence of siltation boom | E | Envirojnmental | 3 | 5 | 15 | B | 1) Install siltation boom / silt skirt with silt curtain 2) Check conenctions between silt skirt and provide geo textile 3) Assign watchman to monitor turbidity generated by the activity | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Spread of turbid water to open sea due to damage siltation boom | E | Envirojnmental | 3 | 5 | 15 | B | 1) Regularly check condition of silt skirt and silt curtain 2) Immediately repair damaged silt curtain | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Dredging vessel running aground due to rough sea condition / high waves | E | Physical / Property | 3 | 5 | 15 | B | 1) Regularly monitor the weather forecast 2) Assign anchor / mooring details to check anchor / mooring condition 3) Suspend activity if waves more than 1.5 meters high, wind speed more than 10 m/s and visibility less than 1Km | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Personnel hit by equipment during operation | E | Physical | 2 | 5 | 10 | B | 1) Strictly control movement of crew during operation 2) Maintain 5 meter distance from working equipment 3) Assign or provide barriers / demarkation line at barge deck | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Personnel slipping on the same level due to materials / slippery deck | E | Physical | 3 | 4 | 12 | B | 1) Maintain cleanliness on the deck 2) Immediately mop and dry wet deck surface | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Environmental pollution due to disposal of bilge / waste materials | E | Environmental | 3 | 5 | 15 | B | 1) No waste must be disposed within 12 nautical miles from the nearest shoreline 2) No HME garbage / waste must be disposed to the sea | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Environmental pollution due to accidental oil / fuel spillage | E | Environmental | 3 | 5 | 15 | B | 1) Store HAZMAT inside vessel compartment / paint locker 2) HAZMAT stored on deck must be properly lashed and with secondary containment 3) Regularly check secondary containment and remove accumulated oil 4) Provide emergency spill kit and regularly conduct drill | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Man falling overboard while working on deck | E | Property | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during operation 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Dredging Works | Unsecured material falling overboard during operation | E | Physical | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Equipment striking vessel structure / crew due to incompetent operator | E | Physical / Property | 3 | 5 | 15 | B | 1) Crane operator experienced and with 3rd party certificate | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Lost of clamshell when using damage / defective equipment | E | Physical / Property | 3 | 5 | 15 | B | 1) Check if crane possess valid 3rd party inspection certificate 2) Check crane condition before use using checklist | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Lost of clamshell bucket to sea due to breaking of wire rope | E | Property | 3 | 5 | 15 | B | 1) Check wire cable and connections 2) Check lifting tackles / safety pins | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Vessel running aground due to rough sea condition / high waves | E | Physical / Property | 3 | 5 | 15 | B | 1) Regularly monitor the weather forecast 2) Assign anchor / mooring details to check anchor / mooring condition 3) Suspend activity if waves more than 5 meters high, wind speed more than 10m/s and visibility less than 1 Km. | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Spread of turbid water to open sea due to absence of siltation boom | E | Envirojnmental | 3 | 5 | 15 | B | 1) Install siltation boom / silt skirt with silt curtain 2) Check conenctions between silt skirt and provide geo textile 3) Assign watchman to monitor turbidity generated by the activity | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Spread of turbid water to open sea due to damage siltation boom | E | Envirojnmental | 3 | 5 | 15 | B | 1) Regularly check condition of silt skirt and silt curtain 2) Immediately repair damaged silt curtain | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Personnel hit by equipment during operation | S | Physical | 2 | 5 | 10 | B | 1) Strictly control movement of crew during operation 2) Maintain 5 meter distance from working equipment | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Personnel slipping on the same level due to materials / slippery deck | S | Physical | 3 | 4 | 12 | B | 1) Maintain cleanliness on the deck 2) Immediately mop and dry wet deck surface | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Man falling overboard while working on deck | S | Property | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during operation 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Unsecured material falling overboard during mooring / anchorin | S | Physical | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Equipment striking vessel structure / crew due to incompetent operator | S | Physical / Property | 3 | 5 | 15 | B | 1) Crane operator experienced and with 3rd party certificate | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Overturning of crane barge due to rough sea condition | S | Physical / Property | 3 | 5 | 15 | B | 1) Suspend lifting operation if waves more than 1.5 meters high, wind speed more than 10m/s and visibility less than 1Km | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Fall of load due to defective lifting gears / lifting equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if crane possess valid 3rd party inspection certificate 2) Check crane condition before use using checklist 3) Check lifting gears and tackles before use | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Fall of load due to unsafe slinging | S | Physical / Property | 3 | 5 | 15 | B | 1) Use proper slinging & padding depending on the load 2) Use designated lifting lugs if available 3) Avoid lifting multiple materials of different configuration | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Fall of load due to improper signalling / incompetent rigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Only assign 3rd party certified rigger to give signal 2) Use radio or ensure hand signal is understood between rigger and crane operator | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) No personnel allowed under the load or crane boom 3) Clear deck of unwanted personnel during lifting operation | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Hitting other structure by load during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Diver hit by load while lowering the pipeline | S | Physical | 3 | 5 | 15 | B | 1) Divers to keep away from load when swinging pipe into place | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Man falling overboard while working on deck | S | Property | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during operation 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Bedding preparation / backfilling works | Unsecured material falling overboard during mooring / anchorin | S | Physical | 3 | 5 | 15 | B | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Diving Works | Drowning / suffering from decompression sickness due to human error | S | Physical | 3 | 5 | 15 | B | 1) Certified and competent divers only 2) Check divers physical and mental condition before each dive 3) Diving operations strictly controlled / supervised by Diving Foreman | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Diving Works | Drowning / suffering from decompression sickness due to equipment failure | S | Physical | 3 | 5 | 15 | B | 1) Check diving equipment and gears before use 2) Use pre-dive checklist before each diving activity | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Diving Works | Struck by suspended pipe during installation to the sea | S | Physical | 3 | 5 | 15 | B | 1) Divers to keep away from load when swinging pipe into place | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Diving Works | Drowning due to absence of buddy diver | S | Physical | 3 | 5 | 15 | B | 1) Maintain buddy system during diving activity 2) Check communication and visual equipment before each dive 3) Assign stand-by diver in case of emergency | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Equipment striking vessel structure / crew due to incompetent operator | S | Physical / Property | 3 | 5 | 15 | B | 1) Crane operator experienced and with 3rd party certificate | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Overturning of crane barge due to rough sea condition | S | Physical / Property | 3 | 5 | 15 | B | 1) Suspend lifting operation if waves more than 1.5 meters high, wind speed more than 10m/s and visibility less than 1Km | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Fall of load due to defective lifting gears / lifting equipment | S | Physical / Property | 3 | 5 | 15 | B | 1) Check if crane possess valid 3rd party inspection certificate 2) Check crane condition before use using checklist 3) Check lifting gears and tackles before use | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Fall of load due to unsafe slinging | S | Physical / Property | 3 | 5 | 15 | B | 1) Use proper slinging & padding depending on the load 2) Use designated lifting lugs if available 3) Avoid lifting multiple materials of different configuration | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Fall of load due to improper signalling / incompetent rigger | S | Physical / Property | 3 | 5 | 15 | B | 1) Only assign 3rd party certified rigger to give signal 2) Use radio or ensure hand signal is understood between rigger and crane operator | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Personnel struck by load when lifting | S | Physical | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) No personnel allowed under the load or crane boom 3) Clear deck of unwanted personnel during lifting operation | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Hitting other structure by load during lifting | S | Physical / Property | 3 | 5 | 15 | B | 1) Use minimum of 2-16mm diamater PP rope at 20m length as tagline 2) Assign worker to hold tagline with knowledge on crane lifting | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Diver hit by load while lowering the pipeline | S | Physical | 3 | 5 | 15 | B | 1) Divers to keep away from load when swinging pipe into place | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Man falling overboard while working on deck | S | Property | 3 | 5 | 15 | B | 1) Restrict vessel crew to roam on deck during operation 2) If unavoidable, buddy system must be imposed and crew wear life jacket | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E
false | Installation of Bell Mouth, Intake Riser, Navigational Bouys and other marine structure | Unsecured material falling overboard during mooring / anchorin | S | Physical | 4 | 5 | 20 | A | 1) No materials except those used for mooring / life saving equipment must remain on deck 2) If no space available inside vessel, ensure materials are properly lashed to prevent possible material falling overboard | Sunyup Moon | 2024-01-15 | 1 | 1 | 1 | E

## 코드목록 (hidden)
구분 | 코드
EHS | E
EHS | H
EHS | S
빈도 Risk Rate | 1
빈도 Risk Rate | 2
빈도 Risk Rate | 3
빈도 Risk Rate | 4
빈도 Risk Rate | 5
강도 Severity | 1
강도 Severity | 2
강도 Severity | 3
강도 Severity | 4
강도 Severity | 5
빈도 Likelihood | 1
빈도 Likelihood | 2
빈도 Likelihood | 3
빈도 Likelihood | 4
빈도 Likelihood | 5
강도 Severity | 1
강도 Severity | 2
강도 Severity | 3
강도 Severity | 4
강도 Severity | 5